This Techno-Economic Viability (TEV) Study and its contents are confidential. Accordingly, this TEV Study and its contents are submitted on the basis that they will be held in complete confidence. By accepting a copy of this report, the recipient agrees to keep its contents and any other information, which is disclosed to such recipient, confidential and shall not divulge, distribute, reproduce, copy or disseminate any information contained herein, in part or in full, without the prior written approval of LSI Financial Services Private Limited (hereinafter referred to as “LSI”) or Serentica Renewables India 9 Private Limited (hereinafter referred to as “SRI9PL”).

This TEV Study has been prepared on the basis of the financial data (Audited Balance Sheets, financial projections etc.), management reports and other information submitted by employees of SRI9PL (‘The Company’) and discussions held with the Company’s officials, historical physical performance of the Company’s Group entities, industry norms, studies and other information/documents obtained by LSI from various sources available publicly, which LSI believes to be reliable. The details, profile & financials of Group companies of SRI9PL included in this TEV Study are based on the documents and other details provided by the company. LSI has not carried out any independent verification for the truthfulness of the same.

This TEV Study constitutes an opinion expressed by LSI and hence, it shall not be held liable for any financial loss incurred by anyone based on this Report. This TEV Study should not be construed as a commitment from LSI for providing any assistance to the Company. LSI, their Board of Directors, employees, officers, executives and affiliates shall not be held responsible in any manner for the contents of this Report or to anybody who acts in any manner for any purpose relying on this matter. The delivery of this TEV Study at any time does not imply that the information in it is correct as of any time after 24-11-2025, or that there has been no change in the operation, financial condition, prospects, creditworthiness, status or affairs of any project or anyone else since that date.

LSI has no obligation to update any information contained in this TEV Study.

This TEV Study is for information only. The opinions expressed may not be suitable to all recipients. Recipients must make their own investigations before acting on the contents of this Report. The TEV Study is divided into chapters & sub-sections only for the purpose of reading convenience. Any partial reading of this Report may lead to inferences, which may be at divergence with the conclusions and opinions based on the entirety of this TEV Study.

All forward-looking statements and/or future projections in this report are based on assumptions considered to be reasonable but the actual outcome may be materially affected by changes in economic and other circumstances, which cannot be foreseen.

This report is not directed or intended for distribution to, or use by, any person or entity who is a citizen or resident of or located in any locality, state, country or other jurisdiction, where such distribution, publication, availability or use would be contrary to law, regulation or which would subject LSI and affiliates to any registration or licensing requirement within such jurisdiction. Persons in whose possession this document may come are required to inform themselves of and to observe such restriction.

Table 1: Site Visit Report	14

Table 2: A gist of the company	22

Table 3: Snapshot of the Promoter	23

Table 4: Gist of the Project	24

Table 5: Key Observations of the Proposal	25

Table 6: Snapshot of the Company	32

Table 7: Capital Structure of the Company as on 22-10-2025	33

Table 8: Shareholding pattern of the Company as on 22-10-2025	35

Table 9: Board of Directors	35

Table 10: Brief Terms of Sanction of REC	36

Table 11: Existing Credit Facilities	40

Table 12: Past Financials of SRI9PL	41

Table 13: Snapshot of Vedanta Limited	45

Table 14: Snapshot of Projects of SRSPL	48

Table 15: Snapshot of Projects of SRIPL	49

Table 16: Snapshot of SRIPL	50

Table 17: Compliance with Master Direction of RBI	55

Table 18: Compliance with Project Finance Direction of RBI	57

Table 19: Compliance Status	57

Table 20: Calculation of Cost Overrun excluding IDC	59

Table 21: Project Snapshot	62

Table 22: Geographical Advantage of Setting up Solar Project in Jaisalmer	65

Table 23: Site Connectivity	66

Table 24: Estimated Land Requirements	67

Table 25: Irradiation Data of the Project Site	69

Table 26: Temperature Data of the Project Site	70

Table 27: Technical Specifications of the Project	71

Table 28: Solar Energy Assessment	73

Table 29: Energy Simulation Assessment	75

Table 30: Projected Generation from Solar Plant	75

Table 31: Captive/ Group Open Access Model	78

Table 32: Brief Snapshot of PDA	79

Table 33: Vedanta Power Demand Analysis	90

Table 34: Landed Cost of Power for VAL	93

Table 35: Brief Term of IA	93

Table 36: Project Implementation Entities	99

Table 37: Key Terms of EPC Contract for the Project	99

Table 38: Key Terms of Shared Infra Agreement for the Project	109

Table 39: Key Terms of the Module Supply Agreement (MSA)	117

Table 40: Project Implementation Schedule	123

Table 41: Status of Approvals	125

Table 42: State Wise Installed Capacity of Solar Power as on 31-10-2024	134

Table 43: Recent Bidding Trends	137

Table 44: Tariff for other Group Captive Projects	138

Table 45: Challenges of Solar Power Plant	139

Table 46: Renewable energy growth drivers	144

Table 47: Components of Project Cost	148

Table 48: Components of EPC Cost	149

Table 49: IDC	150

Table 50: Comparison with Other Solar Projects	151

Table 51: Components of Means of Finance	153

Table 52: Phasing and Source of Promoters Contribution	153

Table 50: Total Commitment of SRSPL	153

Table 51: Indicative INR dominated Terms of Debt	154

Table 55: Indicative INR dominated Term Loan Repayment Sheet	156

Table 52: Indicative USD dominated Terms of Debt	155

Table 56: Indicative USD dominated Term Loan Repayment Sheet	156

Table 55: Critical Risk Factors & Mitigation	158

Table 56: SWOT Analysis	162
Table 57: Sensitivity Analysis	174

INTRODUCTION

Introduction

Serentica Renewables India 9 Private Limited (hereinafter referred to as ‘SRI9PL’ or ‘the Company’) is part of the Vedanta Group founded by Mr. Anil Agarwal. It was incorporated on 30th September’2022 by Serentica Renewables India Private Limited (Promoter or SRIPL), a 100% subsidiary of Serentica Renewables Singapore Private Limited, with an objective of setting up renewable power generation project. The group is a multi-national conglomerate involved in sectors such as Aluminium, Zinc, Lead & Silver, Oil & Gas, Iron Ore, Steel, Copper & Nickel, Power, Ferro Chrome, Semiconductors & Glass.

The groups business operations heavily depend upon 24x7 power availability, thus, making energy security a core to its sustainability. To ensure energy security along with availability of clean and green power, the group established Serentica Renewables Singapore Private Limited (Sponsor or SRSPL) as its Renewable Energy platform to develop, own and operate Renewable Energy projects in India targeting development of projects having capacity of 2.50 GW by 2030. SRSPL is backed by marquee investors (a) Vedanta Group (through Twinstar Overseas Limited) and (b) KKR.

In order to expand its foothold in the renewable power sector along with securing energy security for the group, Serentica Renewables India Private Limited (Promoter or SRIPL) a 100% subsidiary of Serentica Renewables Singapore Private Limited incorporated Serentica Renewables India 9 Private Limited (SRI9PL) on 30th September’2022 with an objective of setting up renewable power generation project. Registered office of the Company is situated at RMZ Infinity, 5th Floor, Plot No. 15, Udyog Vihar, Phase – IV, Palam Road, Gurugram – 122015.

The project entails setting up a Solar Power Generating Project having capacity of 840 MWdc/ 600 MWac located at Kotha & Harba Villages, Tehsil – Fatehgarh, District – Jaisalmer, Rajasthan. REC Limited (REC) had vide its Sanction Letter No. REC/CO/REN/Solar/2023-24/ SRI9PL, dated 16th January’2024, had extended Term Loan facilities of Rs.2971.27 crore at an initial interest rate of 9.45% (pre-COD) and an envisaged SCOD of 30th June’2025 to the company towards financing of Greenfield Solar Power Project having capacity of 900 MWdc/ 600 MWac with an estimated project cost of Rs.3714.09 crore for Captive Consumption to be set up at Fatehgarh, Rajasthan.

Consequent to the above, REC vide its Letter No. REC/CO/REN/2025-26/SRI9PL/92, dated 29th September’2025 based on request of the company have suitably modified the sanction to incorporate revised capacity of the project from initial 900 MWdc/ 600 MWac to 840 MWdc/ 600 MWac, the interest rate to 8.75% (pre-COD) and 8.25% (post-COD), and the SCOD to 30th June’2026 (brief terms of sanction of REC is given in Chapter 2.5.1 of this Report).

Engagement of LSI and Scope of work

In order to assess the Techno Economic Viability (TEV) of Serentica Renewables India 9 Private Limited, India Infrastructure Finance Company Limited (IIFCL), has vide their engagement letter no. IIFCL/SRI9PL/2024-25/2159, dated 22nd October’2025, appointed LSI Financial Services Private Limited (LSI) to conduct a Techno Economic Viability Study.

Scope of Work:

i. Management Evaluation (experience of promoter and management, etc.)

ii. Detailed analysis of Existing Activities of the Company:

About the Company, its background & history

Milestone of the Company

Promoters’ profile

Shareholding Pattern

Board of Directors

Manufacturing Facilities & utilization levels

Business Model

Credit Facilities
Name of Lender(s) Type of Facilities Sanctioned Amount (Rs. Crore) O/s Amount (Rs. Crore)
REC Limited Term Loan 2971.27 1830.31
Yes Bank BG 50.00 30.00
LOC Backed LC 625.00 0.00
Hedging 310.00 215.00
Total 3956.27 2075.31

External Credit Rating
At present no External Credit Rating has been accredited to the Company.

Review Financial Highlights of the Company

iii. Group Profile
The company is part of the Vedanta Group founded by Mr. Anil Agarwal. The group is a multi-national conglomerate involved in sectors such as Aluminium, Zinc, Lead & Silver, Oil & Gas, Iron Ore, Steel, Copper & Nickel, Power, Ferro Chrome, Semiconductors & Glass.

iv. Rationale for setting up new project
The Vedanta Group depends heavily on 24x7 power availability for smooth business operations. To ensure energy security, along with the availability of clean and green power, and to increase its foothold in the renewable energy sector, the group incorporated Serentica Renewables India 9 Private Limited for setting up a Solar Power Generating Project.

v. Feasibility of the New Project
Based on analysis, the project is considered to be Technically Feasible and Financially Viable.

About the Project

Land adequacy
Estimated land requirement for the project is 2300 acres. The company has 2138 acres in possession, with the balance expected to be acquired by December’2025. Surface land requirement per acre of Solar Project complies with prevailing industry standards.

Comments on Project Location
The project is located at Kotha & Harba Villages, Tehsil – Fatehgarh, District – Jaisalmer, Rajasthan, at Latitude 26.40° N and Longitude 70.96° E, with an elevation of 226 meters above Mean Sea Level. The region has a hot arid climate and offers geographical advantages for solar power generation. Overall access to the project site is considered good.

Project Layout

Manufacturing Process

Technical Analysis of the project — comments on technology adopted, consultants appointed / to be appointed for the project, equipment to be used, their make, credential of vendors, etc.
The project adopts high-efficiency monocrystalline bifacial modules (690 Wp N-Type TOPcon Bifacial by Waaree Energies Limited) and 188 central inverter units (3300 kw by Sineng Electric Co. Limited). The modules are mounted on fixed-tilt structures at a 20° angle. OEMs selected for the project are of repute and well established. The plant incorporates a centralized SCADA system for real-time data acquisition, remote control, and predictive maintenance.

Assessment of proposed capacity
The proposed project capacity is 840 MWdc/ 600 MWac.

Product Uses & Application
Power generated from the Solar Plant will be sold to Vedanta Limited (VL) under a Captive Consumption model, through a Power Delivery Agreement.

Industry Analysis (Macro Level) & comments on Marketing Strategy to be adopted by the Company
India's solar power industry shows significant growth, with a potential of 748 GW and 300 sunny days annually. Solar tariffs have become highly competitive, declining from INR 6.2 per kWh in FY2015 to INR 3.1 per kWh in FY2024. The government actively promotes renewable energy through schemes like the Green Energy Corridor, ISTS charges waiver, and must-run status for solar projects. The company's marketing strategy involves selling power to Vedanta Limited (VL) via a Power Delivery Agreement under a captive consumption model.

Raw Material requirement & its sources, tie-up, etc.
The company has secured raw material supply through a Module Supply Agreement (MSA) with Waaree Energies Limited (WAL) for 900 MWdc of Solar PV Modules. WAL will source solar cells as per mutually agreed technical criteria.

Source & Requirement of Utilities

Manpower requirement for the project

Status of Statutory Approvals
Environmental Clearance: Not required as Solar Power Projects fall under White Category; intimation to the State Pollution Control Board suffices.
Intimation to State Pollution Control Board (Rajasthan State Pollution Control Board): Intimated vide letter dated 07-10-2024.
Project Registration (Rajasthan Renewable Energy Corporation Limited (RRECL)): Obtained vide Letter Reference No. RREC/Online/2024/Solar/Cap&O/Serentica-9-02577, dated 29-02-2024 for 600 MWac Solar Power Project.
Land NA Approval (Revenue Department, Government of Rajasthan): Not applicable as per Rajasthan Renewable Energy Policy, 2023, which permits setting up Power Project/Farm on private agriculture land without land conversion.

Comments on Project Implementation Schedule & DCCO (SCOD/COD envisaged as 30th June’2026, with off-taker extension to 22nd August’2026)

Conducting Site visit & provide observations

vi. Validation of Project Cost:

Assessment of Land Development & Civil Cost based on Layout, Drawings (if available),

BOQ and other relevant documents

Assessment of Cost of Plant & Equipment based on quotations / POs / etc (EPC Cost: Rs.2989.08 crore)

Assessment of soft cost & Margin Money for Working Capital (Total Soft Cost: Rs.623.49 crore; Working Capital Margin: Rs.11.79 crore)

Peer comparison, to the extent feasible (Comparison with other Solar Projects performed, confirming project cost is comparable)

vii. Comments on Means of Finance:

Comment on Debt-Equity Ratio (Sanctioned Debt-Equity Ratio: 4:1)

Comments on source of Promoters Contribution (Total envisaged Promoters Contribution: Rs.769.30 crore; Rs.510.39 crore already infused as of 30th September’2025)

Term Loan details – door-to-door tenure, ROI considered, etc (INR Term Loan: 22 years, ROI 8.75% pre-COD, 8.25% post-COD; USD Term Loan: 20 years 9 months, ROI 5.00%)

viii. Financial Feasibility of the project through financial projections:

Comments on Assumptions for financial projections (Detailed assumptions regarding COD, PLF, Tariff, O&M, Taxes, Depreciation, etc., are documented)

Validation of Projected P/L A/c, Balance Sheet, Cash Flow, Term Loan Schedule, etc (Projected statements and schedules are available and implicitly validated)

Calculation of DSCR, IRR, Payback period & Break-Even Point (Average DSCR: 1.43; Minimum DSCR: 1.15)

Ratio Analysis (EBIDTA margins, PAT margin, TOL/TNW, Debt-Equity, Current Ratio,
Debt to EBIDTA, etc (Financial projections provide data for such analysis; Debt-Equity ratio 4:1 as per sanction))

Peer comparison

ix. Strategic Analysis:

SWOT Analysis

Risk-Mitigation

Critical Success Factors

Methodology

Our analysis and assessment have been conducted in the following manner:

Study of documents, data, information, Certified statements and clarification shared by the company’s personnel against the Check List submitted by LSI.

Discussions that LSI has had with the management of, and clarifications given by the company.

Visit to the plant site of the Company.

Collation of Data / information available with LSI.

Extensive research of data/ information available in the public domain.

Conclusions and recommendation on the basis of above analysis.

While all reasonable care has been taken in its preparation, the details contained in this report have been compiled in good faith based on information provided by the company.

It is further informed that no representation, warranty or undertaking, express or implied is made and no responsibility is accepted by LSI Financial Services Private Limited and/or its affiliates and/or its directors, employees/officers in this report or for any direct or consequential loss arising from any use of the information, statements or forecasts in the Report.

Site Visit Report

Apropos the above engagement, Mr. Rudrajit Chowdhury from LSI visited the site on 23rd October’2025. Detail of site visit is provided as under:

Table 1: Site Visit Report

Our Comments:

Based on our site visit, the project is expected to be completed by 22nd August’2026, subject to the company maintains the current pace of work and balance land is acquired by December’2025.

Site Visit Photographs

Executive Summary

Snapshot of the Company

Table 2: A gist of the company
Company Name: Serentica Renewables India 9 Private Limited
Sponsors: Serentica Renewables Singapore Private Limited
Promoters: Serentica Renewables India Private Limited
Date of Incorporation: 30th September’2022
CIN: U40108HR2022PTC106926
Registered Office: RMZ Infinity, 5th Floor, Plot No. 15, Udyog Vihar, Phase – IV, Palam Road, Gurugram – 122015
Capital Structure (as on 22-10-2025):
  Authorised Capital: Rs.323.51 Crore
  Paid-up Capital: Rs.296.51 Crore
Industry: Renewable Energy Generation
Existing Credit Facilities (as on 11-11-2025):
  Sanctioned Amount: Rs.3956.27 Crore
  Outstanding Amount: Rs.2075.31 Crore
External Credit Rating: Not yet accredited

Snapshot of the Promoter

Table 3: Snapshot of the Promoter
Name of the Company: Serentica Renewables India Private Limited
Name of Holding Company: Serentica Renewables Singapore Private Limited
Date of Incorporation: 30th October’2014
CIN: U74110HR2014PTC101972
Registered Office: RMZ Infinity, 5th Floor, Plot No. 15, Udyog Vihar Phase IV, Palam Road, Gurugram – 122015
External Credit Rating (as on 24-09-2025): ICRA AA-(Stable)/ ICRA A1+; Outstanding

Gist of the Project
Project Type: Solar Power Project
Capacity: 840 MWdc/ 600 MWac
Location: Kotha & Harba Villages, Tehsil – Fatehgarh, District – Jaisalmer, Rajasthan
DC to AC Ratio: 1.40
PLF (P90 Level): 20.33% (at DC level) and 28.46% (at AC level)
Land Area: ~2300 acres (2138 acres in possession, balance by December’2025)
Major Equipment Suppliers:
  Solar PV Modules: Waaree Energies Limited
  Inverters: Sineng Electric Co. Limited
Power Offtake: Vedanta Limited (600 MWac, fixed tariff of $ Cents 3.05 per unit for 25 years)
Scheduled Commercial Operation Date (SCOD): 30th June’2026 (extended to 22nd August’2026 by Offtaker)
Total Project Cost: Rs.3846.51 Crore

Table 4: Gist of the Project

Key Observations of the Proposal

Table 5: Key Observations of the Proposal

Project Cost Comparison:

Solar Power:

Source: LSI Internal Data

Our Comments:

The above costs are including GST.

The cost estimated by the Company is comparable with other projects.

THE COMPANY
Serentica Renewables India 9 Private Limited (SRI9PL), part of the Vedanta Group, was incorporated on 30th September 2022 with the objective of setting up renewable power generation projects. Its registered office is at RMZ Infinity, 5th Floor, Plot No. 15, Udyog Vihar, Phase – IV, Palam Road, Gurugram – 122015. As of 22-10-2025, the company has an Authorised Capital of Rs.323.51 Crore and a Paid-up Capital of Rs.296.51 Crore. As on 11-11-2025, outstanding credit facilities total Rs.2075.31 Crore.

Company Profile

Serentica Renewables India 9 Private Limited (hereinafter referred to as ‘SRI9PL’ or ‘the Company’) is part of the Vedanta Group founded by Mr. Anil Agarwal. The group is a multi-national conglomerate involved in sectors such as Aluminium, Zinc, Lead & Silver, Oil & Gas, Iron Ore, Steel, Copper & Nickel, Power, Ferro Chrome, Semiconductors & Glass.

The groups business operations heavily depend upon 24x7 power availability, thus, making energy security a core to its sustainability. To ensure energy security along with availability of clean and green power, the group established Serentica Renewables Singapore Private Limited (Sponsor or SRSPL) as its Renewable Energy platform to develop, own and operate Renewable Energy projects in India targeting development of projects having capacity of 2.50 GW by 2030. SRSPL is backed by marquee investors (a) Vedanta Group (through Twinstar Overseas Limited) and (b) KKR.

In order to expand its foothold in the renewable power sector along with securing energy security for the group, Serentica Renewables India Private Limited (Promoter or SRIPL) a 100% subsidiary of Serentica Renewables Singapore Private Limited incorporated Serentica Renewables India 9 Private Limited (SRI9PL) on 30th September’2022 with an objective of setting up renewable power generation project. Registered office of the Company is situated at RMZ Infinity, 5th Floor, Plot No. 15, Udyog Vihar, Phase – IV, Palam Road, Gurugram – 122015.

A brief snapshot about the company is provided as under:

Table 6: Snapshot of the Company

Existing Business Operations

The company has been formed with an objective to set up Renewable Energy Project and at present it does not have any existing business operations.

Capital Structure and Shareholding Pattern

The capital structure of the company as on 22.10.2025 is as under:

Table 7: Capital Structure of the Company as on 22-10-2025

Source: MCA Website/ Company Information

Shareholding pattern of the company

Table 8: Shareholding pattern of the Company as on 22-10-2025

Source: MCA Website/ Company Information

Board of Directors

The board of directors of the Company are as under:

Table 9: Board of Directors

Source: MCA Website/ Company Information

Brief Profile of Directors is provided as under:

Amarendranath Tatimakula Reddy– T.A.N. Reddy has over 25 years of experience in policy, regulatory affairs, and business development across the power and infrastructure sectors. As Director and Chief Officer – Business Regulatory, he leads the company’s engagement with policymakers and regulators, driving strategies that enable project development, compliance, and sectoral growth. He has been instrumental in shaping Sterlite’s grid and infrastructure businesses since their inception within the Vedanta Group.

Lakshmi Narayan Venkat Ramanan – From VIT to Cornell University, Lakshmi Narayan Venkatramanan blends a strong technical foundation in Chemical Engineering with advanced expertise in Engineering Management & Finance — a perfect mix of analytical precision and strategic acumen driving India’s renewable energy transition.

Amit Ramnani - Amit Ramnani is a senior finance executive with over 20 years of experience in renewable energy, infrastructure finance, and strategic operations. At Serentica, he oversees financial strategy, project finance, procurement, and risk management across a 6 GW portfolio with a roadmap to 17 GW by FY 2030. Previously Head of Corporate Finance & Treasury at Sterlite Power, he has a strong background in capital raising, M&A, and governance, bridging strategic decision-making with on-ground execution in large-scale infrastructure projects.

Credit Facilities and Rating

Details regarding Credit Facilities and Rating is given below:

Project Funding – REC Limited

REC Limited (REC) vide its Sanction Letter No. REC/CO/REN/Solar/2023-24/ SRI9PL, dated 16th January’2024, had extended Term Loan facilities of Rs.2971.27 crore to the company towards financing of Greenfield Solar Power Project having capacity of 900 MWdc/ 600 MWac for Captive Consumption to be set up at Fatehgarh, Rajasthan with an envisaged SCOD of 30th June’2025.

Consequent to the above, REC vide its Letter No. REC/CO/REN/2025-26/SRI9PL/92, dated 29th September’2025 based on request of the company have suitably modified the sanction to incorporate revised capacity of the project from initial 900 MWdc/ 600 MWac to 840 MWdc/ 600 MWac along with revised SCOD of 30th June’2026.

A brief snapshot of the Sanctioned Terms of REC is given below:

Table 10: Brief Terms of Sanction of REC
Particulars             Details
Purpose of the Loan     To fund the debt portion of 600 MWac/ 840 MWdc Greenfield 
                        Solar Project to be setup at Fatehgarh, Rajasthan for captive 
                        consumption being developed by M/s. Serentica Renewables 
                        India 9 Private Limited (SRI9PL)
Name of Borrower        Serentica Renewables India 9 Private Limited
Estimated Project Cost  Rs.3714.09 crore
Debt-Equity Ratio       4:1, contemplating to Term Loan of Rs.2971.27 crore and 
                        Promoters Contribution of Rs.742.82 crore
Maximum Working 
Capital Limit Loan      Rs.50.00 crore
Rate of Interest        9.45%
SCOD                    30-06-2026
Loan Availability Period From the date of loan documentation until earlier of Scheduled 
                        Commercial Operation Date (SCOD) +12 months or Commercial 
                        Operation Date (COD) + 12 months, whichever is earlier
Prepayment Charges      Following are the Prepayment Charges as per the Sanction 
                        Letter:

                         2.00 %, if the prepayment is made within 3 years from the 1st 
                          Disbursement.
                         1.50%, if the prepayment is made after 3 years and up to 5 
                          years from the 1st Disbursement.
                         1.00%, if the prepayment is made after 5 years and up to 10 
                          years from the 1st Disbursement.
                         0.50%, if the prepayment is made after 10 years from the 1st 
                          Disbursement.

                        In case of the prepayment through External Commercial 
                        Borrowing, prepayment charges of 1.00% shall be levied, if the 
                        prepayment is made after 3 years and within 10 years from the 
                        1st Disbursement.

                        Prepayment charges shall not be applicable in the following 
                        cases:

                         Effected at the instance of REC.
                         If paid out of Internal Accruals or Promoters Own Sources 
                          (Equity/ IPO/ Bonds/ InvIT).
                         Due to cash sweep (if applicable) by lender(s).
                         When paid out of Insurance Proceeds/ LD/ etc.
                         If paid out of Capital Subsidy/ Grant.
Submission of External 
Credit Rating & Post 
COD Rebate               A rebate of 25 BPS on applicable interest rate shall be allowed 
                          after the project is fully commissioned. The rebate shall be 
                          effective after 6 months of satisfactory commercial 
                          operations post COD.
                         Borrower needs to get itself rated within one year after COD 
                          and shall submit external credit rating (not less than 
                          investment grade) at least once every year post COD. The 
                          credit rating should have been done by SEBI/RBI accredited 
                          agencies only.
                         Any non-compliance pertaining to submission of external 
                          credit rating leads to withdrawal of interest rate rebate thus 
                          provided.
Repayment of Loan      Moratorium Period: 12 months from SCOD or COD whichever 
                          is earlier.
                         Repayment Period: 228 structured monthly installments.
Assignment and Transfer REC is at liberty to sell down/novate/assign, entire or any part 
                        of this Rupee Term Loan including all rights and benefits 
                        hereunder or transfer or coveted, all or part of its rights that 
                        has accrued/will accrue to REC, all benefits and obligations 
                        under the financing and/or security documents to which REC is 
                        a party, to any person or institution, including Bank, Financial 
                        Institution, Securitization/Reconstruction Company or to any 
                        other Third Party as may be desired by REC.

                        REC shall be fully empowered to assign the debt and the benefit 
                        of this loan, guarantees and the securities to be created for the 
                        loan to the Government of India, RBI or any other institution as 
                        security of any refinance/arrangement which may be worked 
                        out by REC with such organization in respect of the loan. The 
                        Borrower shall, as and when required by REC, join in doing and 
                        executing all such acts, deeds, documents and assurances as 
                        REC may require to give effect to such assignment.
Promoter Undertaking The Promoters shall undertake the following:

                         To bring in further as required equity from own sources in 
                          case of cost overrun without recourse to lenders and of project 
                          assets. Any penalties/liquidated damages for delay in execution 
                          of the project if any over and above Project Cost, beyond the 
                          stipulated period in the Power Purchase.
                         Impact of any change in regulations/ rules/ acts/ statutes or 
                          levying of any charges/ fines/ penalties by any regulatory/ 
                          statutory body or suspension/ cessation of operations in 
                          respect to the project, over and above Project Cost have to be 
                          borne by Promotor
                         To comply with all CPs as per PPA. In case of non-compliance 
                          of CPs, any penalty/financial liability on the Borrower, over 
                          and above Project Cost, shall be borne by promoters without 
                          any recourse to the project asset
                         Promoter / Sponsor shall comply with all the conditions in all 
                          the Project documents, loan documents related to the 
                          Promoter/ Sponsor and in various statutory & non-statutory 
                          clearances/ approvals of the Project, whichever applicable
                         Promoter shall undertake that in the event of any shortfall of 
                          project funding due to default of any other Promoter/ 
                          Lenders, Promoter shall contribute the entire amount of short 
                          fall to the satisfaction of REC from their own resources in form 
                          of equity subscription or any other means allowed under the 
                          prevailing Law, without recourse to Lender; [Not applicable for 
                          A (+/-) rated Borrower/Promoter]
                         Vedanta has to submit the legal biding undertaking for 
                          assignment of Power Delivery Agreement (PDA) and to comply 
                          the obligation of the respective PDA
                         Promoter (Serentica Renewables India Private Limited) will 
                          submit legally binding undertaking, that any shortfall to meet 
                          the debt obligations of REC during the tenure of loan, will be 
                          borne by the Promoter without any recourse to the project 
                          assets
                         Serentica Renewables India Private Limited shall undertake 
                          to provide necessary financing to fund all:
                             Base Equity Requirement.
                             Cost Overruns in the Project.
                             Obligations of the Borrower under the Facility Agreement 
                              until the actual annual DSCR is ≥ 1.20x for any full financial 
                              year post COD. This is allowed to be based on unaudited 
                              financial statement of the Borrower and certified by an 
                              independent Chartered Accountant
DSRA                     DSRA equivalent to at least one quarter peak of interest and 
                          principal shall be created on or before COD:
                         DSRA may be created by providing BG/ or depositing cash 
                          equivalent into TRA/ or by way of loan disbursement in case 
                          DSRA is funded as a part of sanction amount by REC.
                         The Promoter shall have the option to replace 1 quarter 
                          equivalent of cash DSRA with a Bank Guarantee of equal 
                          amount during the tenure of the facility, except when DSRA is 
                          created by funding as part of sanction by REC.
                        [Borrowing companies shall also create additional reserves 
                          as may be stipulated by REC based on appraisal]
Capital Structure       Permitted Capital Structure as per the Sanction is:

Instruments             Breakup

Equity Shares           Minimum 25%
OCRPS/ CCDs             Minimum 26%
NCDs                    Maximum 49%
Total                   100%

Table 10: Brief Terms of Sanction of REC
Particulars
Details
Purpose of the Loan
To fund the debt portion of 600 MWac/ 840 MWdc Greenfield
Solar Project to be setup at Fatehgarh, Rajasthan for captive
consumption being developed by M/s. Serentica Renewables
India 9 Private Limited (SRI9PL)
Name of Borrower
Serentica Renewables India 9 Private Limited
Estimated Project
Cost
Rs.3714.09 crore
Debt-Equity Ratio
4:1, contemplating to Term Loan of Rs.2971.27 crore and
Promoters Contribution of Rs.742.82 crore
Maximum Working
Capital Limit Loan
Rs.50.00 crore
Rate of Interest
9.45%
SCOD
30-06-2026
Loan Availability
Period
From the date of loan documentation until earlier of Scheduled
Commercial Operation Date (SCOD) +12 months or Commercial
Operation Date (COD) + 12 months, whichever is earlier
Prepayment
Charges
Following are the Prepayment Charges as per the Sanction
Letter:

 2.00 %, if the prepayment is made within 3 years from the 1st
Disbursement.
 1.50%, if the prepayment is made after 3 years and up to 5
years from the 1st Disbursement.
 1.00%, if the prepayment is made after 5 years and up to 10
years from the 1st Disbursement.
 0.50%, if the prepayment is made after 10 years from the 1st
Disbursement.

In case of the prepayment through External Commercial
Borrowing, prepayment charges of 1.00% shall be levied, if the
prepayment is made after 3 years and within 10 years from the
1st Disbursement.

Prepayment charges shall not be applicable in the following
cases:

 Effected at the instance of REC.
 If paid out of Internal Accruals or Promoters Own Sources
(Equity/ IPO/ Bonds/ InvIT).
 Due to cash sweep (if applicable) by lender(s).
 When paid out of Insurance Proceeds/ LD/ etc.
 If paid out of Capital Subsidy/ Grant.
Submission of
External Credit
Rating & Post COD
Rebate
 A rebate of 25 BPS on applicable interest rate shall be allowed
after the project is fully commissioned. The rebate shall be
effective after 6 months of satisfactory commercial
operations post COD.
 Borrower needs to get itself rated within one year after COD
and shall submit external credit rating (not less than
investment grade) at least once every year post COD. The
credit rating should have been done by SEBI/RBI accredited
agencies only.
 Any non-compliance pertaining to submission of external
credit rating leads to withdrawal of interest rate rebate thus
provided.
Repayment of Loan
 Moratorium Period: 12 months from SCOD or COD whichever
is earlier.
 Repayment Period: 228 structured monthly installments.
Assignment and
Transfer
REC is at liberty to sell down/novate/assign, entire or any part
of this Rupee Term Loan including all rights and benefits
hereunder or transfer or coveted, all or part of its rights that has
accrued/will accrue to REC, all benefits and obligations under
the financing and/or security documents to which REC is a party,
to any person or institution, including Bank, Financial
Institution, Securitization/Reconstruction Company or to any
other Third Party as may be desired by REC.

REC shall be fully empowered to assign the debt and the benefit
of this loan, guarantees and the securities to be created for the
loan to the Government of India, RBI or any other institution as
security of any refinance/arrangement which may be worked
out by REC with such organization in respect of the loan. The
Borrower shall, as and when required by REC, join in doing and
executing all such acts, deeds, documents and assurances as REC
may require to give effect to such assignment.
Promoter
Undertaking
The Promoters shall undertake the following:

 To bring in further as required equity from own sources in
case of cost overrun without recourse to lenders and of
project assets. Any penalties/liquidated damages for delay in
execution of the project if any over and above Project Cost,
beyond the stipulated period in the Power Purchase.
 Impact of any change in regulations/ rules/ acts/ statutes or
levying of any charges/ fines/ penalties by any regulatory/
statutory body or suspension/ cessation of operations in
respect to the project, over and above Project Cost have to be
borne by Promotor
 To comply with all CPs as per PPA. In case of non-compliance
of CPs, any penalty/financial liability on the Borrower, over
and above Project Cost, shall be borne by promoters without
any recourse to the project asset
 Promoter / Sponsor shall comply with all the conditions in all
the Project documents, loan documents related to the
Promoter/ Sponsor and in various statutory & non-statutory
clearances/ approvals of the Project, whichever applicable
 Promoter shall undertake that in the event of any shortfall of
project funding due to default of any other Promoter/
Lenders, Promoter shall contribute the entire amount of
short fall to the satisfaction of REC from their own resources
in form of equity subscription or any other means allowed
under the prevailing Law, without recourse to Lender; [Not
applicable for A (+/-) rated Borrower/Promoter]
 Vedanta has to submit the legal biding undertaking for
assignment of Power Delivery Agreement (PDA) and to
comply the obligation of the respective PDA
 Promoter (Serentica Renewables India Private Limited) will
submit legally binding undertaking, that any shortfall to meet
the debt obligations of REC during the tenure of loan, will be
borne by the Promoter without any recourse to the project
assets
 Serentica Renewables India Private Limited shall undertake
to provide necessary financing to fund all:

 Base Equity Requirement.
 Cost Overruns in the Project.
 Obligations of the Borrower under the Facility Agreement
until the actual annual DSCR is ≥ 1.20x for any full financial
year post COD. This is allowed to be based on unaudited
financial statement of the Borrower and certified by an
independent Chartered Accountant
DSRA
 DSRA equivalent to at least one quarter peak of interest and
principal shall be created on or before COD:
 DSRA may be created by providing BG/ or depositing cash
equivalent into TRA/ or by way of loan disbursement in case
DSRA is funded as a part of sanction amount by REC.
 The Promoter shall have the option to replace 1 quarter
equivalent of cash DSRA with a Bank Guarantee of equal
amount during the tenure of the facility, except when DSRA is
created by funding as part of sanction by REC.
[Borrowing companies shall also create additional reserves
as may be stipulated by REC based on appraisal]
Capital Structure
Permitted Capital Structure as per the Sanction is:

Instruments
Breakup
Equity Shares
Minimum 25%
OCRPS/ CCDs
Minimum 26%
NCDs
Maximum 49%
Total
100%

Current Outstanding Credit Facilities and Rating

Details of Existing Credit Facilities of the Company as on 11th November’2025 is given below:

Table 11: Existing Credit Facilities
Name of Lender(s)
Type of Facilities
Sanctioned
Amount (Rs.
Crore)
O/s Amount (Rs.
Crore)
REC Limited
Term Loan
2971.27
1830.31
Yes Bank
BG
50.00
30.00
LOC Backed LC
625.00
0.00
Hedging
310.00
215.00
Total
3956.27
2075.31
Source: Company Information

Source: Company Information

At present no External Credit Rating has been accredited to the Company.

Past Financials of SRI9PL

Details regarding past financials of SRI9PL is given below:

Table 12: Past Financials of SRI9PL
Particulars
Rs. in crore unless otherwise specified
FY25
FY24
Revenue from Operations
0.00
0.00
Other Income
3.46
0.00
Total Income
3.46
0.00
Profit Before Tax (PBT)
2.18
-1.18
Profit After Tax (PAT)
-2.32
-1.66
Total Equity
289.76
133.97
Total Outside Liabilities (TOL)
1734.65
224.66
Tangible Net Worth (TNW)
289.76
133.97
TOL/ TNW
5.98
1.67
Current Assets
332.86
347.76
Current Liabilities
310.55
10.25
Current Ratio
1.07
33.92
Source: Audited Balance Sheets

Source: Audited Balance Sheets

Our Comments:

The Company is in the process of setting up a Solar Power Generating Plant and thus at present does not have any Revenue from Operations.

Other Income of Rs.3.46 crore represents Marked to Market Gain earned in terms of Hedge Contracts.

During FY25, the company raised Rs.65.00 crore of Equity Share Capital by way issuance of Fresh Equity of Rs.45.00 crore and Rs.20.00 crore by way of Conversion of CCDs into equity. Further during the year, the company has issued Optionally Convertible Redeemable Preference Share Capital of Rs.75.00 crore.

The company does not have any Contingent Liability as on FY25.

PROMOTER GROUP DETAILS

Group Profile

The company is part of the Vedanta Group founded by Mr. Anil Agarwal. The group is a multi-national conglomerate involved in sectors such as Aluminium, Zinc, Lead & Silver, Oil & Gas, Iron Ore, Steel, Copper & Nickel, Power, Ferro Chrome, Semiconductors & Glass. Operating structure of the group is depicted below:

Exhibit – Operating Structure of the Vedanta Group

The Vedanta Group is a market leader in the Zinc – Lead – Silver Industry (with 77% market share in India) and Aluminium Industry (with 48% market share in India). The groups business operations heavily depend upon 24x7 power availability, thus, making energy security a core to sustainability. To ensure energy security along with availability of clean and green power, the group established Serentica Renewables Singapore Private Limited (Sponsor or SRSPL) as its Renewable Energy platform to develop, own and operate Renewable Energy projects in India targeting development of projects having capacity of 17 GW by FY 2030. SRSPL is backed by marquee investors (a) Vedanta Group (through Twinstar Overseas Limited) and (b) KKR.

A chart depicting corporate structure of Serentica Renewables India 9 Private Limited is given below:

Vedanta Group

Vedanta Group founded by Mr. Anil Agarwal is a multi-national conglomerate involved in sectors such as Aluminium, Zinc, Lead & Silver, Oil & Gas, Iron Ore, Steel, Copper & Nickel, Power, Ferro Chrome, Semiconductors & Glass. Vedanta Limited is the flagship company of the group, clocking a Consolidated Revenue from Operations of Rs.152968 crore as of FY25 with an Operating EBIDTA of Rs.42343 crore. Outcomes of the key segments of the group as on FY25 is produced below:

A brief snapshot of Vedanta Limited (Flagship Company of the Group) is given below:

Table 13: Snapshot of Vedanta Limited

KKR

KKR is a global investment firm investing across Private Markets in every asset class all over the world. KKR serves (i) Institutional Investors, (ii) Global Wealth, (iii) Family Capital and (iv) Companies.

KKR has over 49 years of investment experience having ~USD 686 Billion in AUM across Credit & Liquid Strategies, Private Equity and Real Estates as on Qtr.2 of Calander Year 2025. A diagrammatic representation of the growth story of KKR is depicted below:

Serentica Renewables (Singapore) Private Limited

Serentica Renewables (Singapore) Private Limited (hereinafter referred to as Sponsor or SRSPL) is the Renewable Energy Arm of the Vedanta Group. SRSPL was incorporated on 25th November’2022 with an objective of Generation of Electricity from Renewable Sources. Registered office of SRSPL is situated at 23, Church Street, #07-00, Capital Square, Singapore – 049481.

A brief snapshot of Serentica Renewables Singapore Private Limited is given below:

Table 14: Snapshot of Projects of SRSPL

Particulars 
Details 
Name 
of 
the 
Company 
Serentica Renewables (Singapore) Private Limited 
Company 
Registration 
Number 
202242188E 
Date 
of 
Incorporation 
25th November’2022 
Registered Office 23, Church Street, #07-00, Capital Square, Singapore – 049481 
Board 
of 
Directors 
SN 
Name of Director 
1 
Madhura Narawane 
2 
Pratik Agarwal 
3 
Goh Ping Hao 
4 
Ananya Gupta 
Consolidated 
Past Financials of
Particulars 
Amounts in US$ million 
unless otherwise specified 
31st 
March’2024 
31st 
March’2023 
Revenue from Operations 
4.28 
-0.01
-0.65 
-0.42 
Profit Before Tax (PBT) 
-1.54 
-0.50 
Profit After Tax (PAT) 
-4.33 
-0.50 
Tangible Net Worth (TNW) 
420.83 
69.54 
Total Outside Liabilities (TOL) 
11.17 
8.09 
Investment in Subsidiaries 
213.86 
72.34 
Current Assets 
25.54 
5.29 
Current Liabilities 
0.21 
0.09

Serentica Renewables India Private Limited

Serentica Renewables India Private Limited (hereinafter referred to as ‘Promoter’ or ‘SRIPL’) is a 100% Subsidiary of Serentica Renewables Singapore Private Limited. SRIPL at present is developing ~5478 MW of renewable energy projects across Karnataka, Maharashtra & Rajasthan.

Details of projects implemented/ under implementation by SRIPL through its various SPVs is given below:

Table 15: Snapshot of Projects of SRIPL
SN 
SPV
Offtaker 
Capacity 
(MW AC) 
Type 
Solar 
(DC) 
Solar (AC) 
Wind (AC) 
Total 
MW 
Capacity 
Commissioned 
(AC) 
1 
SRIPL 1
BALCO
200 
Hybrid 
252.5 
189 
204 
457 
188.27 MW - 
Solar 
2 
SRIPL 3 
Vedanta Ltd. 
221 
Hybrid 
263 
200 
270 
533 
110 MW - Solar 
& Wind 
3 
SRIPL 4
HZL
200 
Hybrid 
243 
168 
320 
563 
168 MW - Solar 
4 
SRIPL 5
HZL
250 
Hybrid 
337 
232 
370 
707 
220 MW - Solar 
5 
SRIPL6 
Vedanta Ltd 
50 
Hybrid 
53 
37 
65 
118 
- 
6 
SRIPL7
BALCO
105 
Hybrid 
109 
75 
106 
215 
- 
7 
SRIPL8
BALCO
200 
Solar 
280 
200 
 - 
280 
- 
8 
SRIPL9 
Vedanta Ltd 
600 
Solar 
840 
600 
 - 
840 
- 
9 
SRIPL 14 
Hindustan Zinc 
Limited 
80 
Hybrid 
211 
141 
285 
496 
- 
10 
SRIPL 19 
Inox Air 
Products Pvt. 
Ltd. 
22.5 
Hybrid 
38.4 
25.6 
36.3 
75 
- 
11 
SRIPL 20
NTPC
200 
Hybrid 
500 
250 
200 
700 
- 
12
NHPC
150 
Hybrid 
270 
180 
225 
495 
- 
Total 
5,478

Source: Company Information

A brief snapshot of SRIPL is given below:

Table 16: Snapshot of SRIPL 
Particulars 
Details 
Name of the Company 
Serentica Renewables India Private Limited 
Name of Holding 
Company 
Serentica Renewables Singapore Private Limited 
Date of Incorporation 
30th October’2014
U74110HR2014PTC101972 
Registered Office 
RMZ Infinity, 5th Floor, Plot No. 15, Udyog Vihar Phase IV, 
Palam Road, Gurugram – 122015 
Board of Directors 
Details of Board of Directors of SRIPL is given below: 

Name of Director
Designation 
Akshay Pradeep Hiranandani 
07557700 
Director 
Simrun Mehta 
09118938 
Director 
Pratik Pravin Agarwal 
03040062 
Director 
Ravi Thanvi 
09631208 
Additional 
Director 
External Credit Rating 
ICRA Ratings have accredited SRIPL with the following 
Credit Rating as on 24-09-2025: 

Instrument 
Rated Amount 
(Rs. Crore) 
Rating Action 
Long Term/ Short 
Term 
– 
Fund 
Based/ Non-Fund 
Based Limits 
535.00 
ICRA AA-
(Stable)/ ICRA 
A1+; Outstanding 
Long Term/ Short 
Term 
Non-Fund 
Based Limits 
650.00 
ICRA AA-
(Stable)/ ICRA 
A1+; Outstanding 
Long Term/ Short 
Term 
– 
Unallocated Limits 
15.00 
ICRA AA-
(Stable)/ ICRA 
A1+; Outstanding 
Total 
1200.00

Table 16: Snapshot of SRIPL

Board of Directors (SRIPL)

Details of Board of Directors of SRIPL is given below:

Source: MCA

Brief profile of the above Board of Directors is given below:

Akshay Pradeep Hiranandani - At Serentica, Mr. Akshay heads the Corporate Finance division, overseeing capital raising and allocation strategies for the company’s sustainable energy platform, which is committed to delivering round-the-clock green power to some of India’s largest industrial consumers. With nearly two decades of experience — including over fifteen years in Corporate Finance and Project Development — he has successfully raised more than USD 1.5 billion through debt and equity for both domestic and international renewable energy developers. He has also led the development and execution of over 1 GW of renewable energy projects. Before joining Serentica, Mr. Akshay led the Structured Investments and Project Finance vertical at Piramal Capital, where he managed, deployed, and exited investments totalling approximately USD 1 billion in infrastructure.

Simrun Mehta – Ms. Simrun Mehta is a Director with KKR’s Private Equity team, having joined the firm in 2012. She plays a key role in driving KKR’s investments in India, particularly across the consumer, retail, and healthcare sectors. Over the years, she has been actively involved in several of KKR’s investments spanning diverse industries.

Ms. Mehta currently serves on the boards of Vini Cosmetics, Lighthouse Learning, Avendus Capital, RE Sustainability, Ness Digital Engineering, and Serentica Renewables. Before joining KKR, she worked with Nomura’s fixed income division and earlier with the commodities team at Lehman Brothers. She holds a Bachelor of Arts (Honours) degree in Mathematics from St. Stephen’s College.

Pratik Pravin Agarwal – Mr. Pratik Agarwal is the Chairman of Serentica Renewables, a green energy company dedicated to delivering round-the-clock, carbon-free power to India’s large industrial consumers. He also serves as the Managing Director of Sterlite Power and is a Non-Executive Director at Sterlite Technologies Limited and Sterlite Investment Managers Ltd. and Serentica Renewables (Singapore) Private Limited Previously, he has held directorial positions at Sterlite Ports, Vizag General Cargo Berth Ltd, and Speedon Networks Limited, while also leading Vedanta Group’s investor relations and strategic initiatives. Vedanta Limited is a diversified natural resources company with annual revenues of approximately USD 17 billion. He holds a Bachelor of Science degree from the Wharton School, University of Pennsylvania, and an MBA from the London Business School.

Ravi Thanvi – Mr. Ravi Thanvi is an Additional Director at SRIPL and a Principal with KKR’s Asia-Pacific Infrastructure team, based in Mumbai, where he oversees the firm’s energy investments in India. He brings over 13 years of experience in private equity and investment banking, specializing in the energy and infrastructure sectors across India and Southeast Asia. Before joining KKR, Mr. Ravi spent six years at Actis, where he played a pivotal role in expanding the firm’s energy and infrastructure portfolio in India and Southeast Asia. During his tenure, he helped deploy over USD 1 billion across projects in renewables, gas, and toll roads. Earlier in his career, he worked in investment banking at Goldman Sachs and HSBC, advising global clients on mergers and acquisitions as well as strategic fundraising related to investments in India. Mr. Ravi holds a Master’s degree in Mathematics from the Indian Institute of Technology, Kharagpur (IIT-KGP) and an MBA from the Indian Institute of Management, Ahmedabad (IIM-A).

Past Financials of SRIPL

Past Financials of SRIPL is given below:

Source: Audited Balance Sheet

Our Comments:

Revenue from Operations: SRIPL is in the business of build, own, manage, operate and maintain hydel, solar, wind, geothermal and other renewable energy power projects. SRIPL primarily earns its Revenue from Operations by providing EPC Services and Management Fee Income. During FY25, revenue from operations increased multifold to Rs.797.14 crore from Rs.142.55 crore in FY24. The increase is mainly due to revenue booked from EPC Services amounting to Rs.637.28 crore.

Other Income: Other Income earned during FY25 was Rs.78.09 crore. This primarily constitutes Interests on Bank Deposits amounting to Rs.45.46 crore and Interests on Loan given to Related Parties amounting to Rs.31.99 crore.

EBIDTA: Even though Revenue from Operations of SRIPL increased from Rs.142.55 crore in FY24 to Rs.797.14 crore in FY25, EBIDTA levels dropped from being at 46.18% in FY24 to 19.62% in FY25. Primary reason attributable to drop in EBIDTA levels is increase in Employee Benefit Expenses (from Rs.33.41 crore in FY24 to Rs.67.88 crore in FY25) and increase in Other Expenses (from Rs.53.19 crore in FY24 to Rs.81.51 crore in FY25).

Total Equity: Total Equity of SRIPL increased from Rs.666.21 crore to Rs.801.92 crore backed by ploughing back of profits during the year.

Total Outside Liabilities (TOL): TOL of SRIPL increased from Rs.756.36 crore to Rs.2344.26 crore. This can primarily be attributed towards increase in Other Current Liabilities rising to Rs.1267.90 crore in FY25 from Rs.5.77 crore in FY24. Other Current Liabilities primarily constitutes of Rs.1239.05 crore being Advance from Customers.

TOL/ TNW: TOL/ TNW of SRIPL has increased from 1.14 times in FY24 to 2.92 times in FY25 primarily due to increase in Other Current Liabilities.

Current Ratio: Current Ratio of SRIPL dropped to 0.90 times in FY25 from being at 1.40 times in FY24. This is majorly due to increase in Short Term Borrowings and Other Current Liabilities.

Contingent Liabilities: SRIPL does not have any Contingent Liabilities as on 31st March’2025.

RBI GUIDELINE

RBI Guideline

For the applicability of RBI Circular and Norms related to the proposed project finance, we have referred following circulars:

Master Direction – Reserve Bank of India (Transfer of Loan Exposures) Directions, 2021 (RBI/DOR/2021-22/86 - DOR.STR.REC.51/21.04.048/2021-22 -dated 24th September 2021, updated on 28th December 2023).

Also, due to change in project cost and loan amount, following RBI notification has been referred:

Notification - RBI/2025-26/59 - DOR.STR.REC.34/21.04.048/2025-26 -dated 19th June 2025, effective from 01st October 2025.

Compliance status of Master Direction – Reserve Bank of India (Transfer of Loan Exposures) Directions, 2021 dated 24th September 2021, updated on 28th December 2023:

Table 17: Compliance with Master Direction of RBI (Transfer of Loan Exposures)

RBI, Project Finance Directions, 2025 dated 19th June 2025 which is effective from 01st October 2025:

Table 18: Compliance with Project Finance Direction of RBI

Compliance Status

Table 19: Compliance Status

Table 20: Calculation of Cost Overrun excluding IDC

PROJECT DESCRIPTION

Project Description

Vedanta Group a multi-national conglomerate operating in various sectors depends heavily on 24x7 power availability to ensure smooth business operations. The group in order to have energy security along with availability of clean and green power and to increase its foothold in the renewable energy sector have incorporated Serentica Renewables India 9 Private Limited for setting up a Solar Power Generating Project having capacity of 840 MWdc/ 600 MWac located at Kotha & Harba Villages, Tehsil – Fatehgarh, District – Jaisalmer, Rajasthan.

Project Snapshot

A brief snapshot of the proposed project is provided as under:

Table 21: Project Snapshot
Particulars                     Details
Project                         Setting up a Solar Power Project having Capacity of 840 MWdc/ 600
                                MWac located at Kotha & Harba Villages, Tehsil – Fatehgarh,
                                District – Jaisalmer, Rajasthan
Location of the Project         Location of the project is described as under:

                                Particulars     Details
                                Villages        Kotha & Harba
                                Tehsil          Fatehgarh
                                District        Jaisalmer
                                State           Rajasthan
                                Latitude        26.40° N
                                Longitude       70.96° E
Land                            The project is being set up on Lease Hold Land admeasuring ~2300
                                acres.

                                At present the company has in its possession 2138 acres of land,
                                balance portion is expected to be acquired by December’2025.
Project Capacity                The present proposal entails setting up the following capacity:

                                Particulars     MWdc    MWac    DC to AC
                                                                Ratio   PLF at P90
                                Project         840     600     1.40    20.33% (at DC level)
                                Capacity                                and 28.46% (at AC
                                                                        level)
Power Evacuation                Power generated from the project shall be evacuated at 400 kV
                                Evacuation voltage level at CTU of Fatehgarh Rajasthan. The total
                                connectivity maximum capacity as approved by CTU is 900 MW.

                                400/33kV plant switchyard shall have two transformer bay, two main
                                bus, one bus coupler and one line bay for the 400kV S/C TL to connect
                                to CTU (approx. 12.50 km)
Transmission Line               The project involves construction of 400kV having 36 towers with a
                                Stringing Length of 12.50 kms.

                                As per project progress as on 31st October’2025, out of the total 36
                                towers, Foundation of 34 towers has been completed, also ROW for 34
                                out of 36 towers is also in possession. Further, Erection of 18 towers is
                                completed.

                                Stringing of 0.05 km out of 12.50 km is completed.
Major Equipment Specifications  The major equipment specification forming part of the Solar Power
                                Plant is provided as under:

                                Particulars     Details
                                Solar PV Modules        690 Wp N-Type TOPcon Bifacial supplied by
                                                        Waaree Energies Limited
                                Inverter                3300 kw Central Inverters supplied by Sineng
                                                        Electric Co. Limited
Power Offtake                   Power generated from the Solar Plant will be sold to Vedanta Limited
                                (VL). A Power Delivery Agreement (PDA) has been executed between
                                SRI9PL and VL for offtake of 600 MWac of Contracted Capacity under
                                Captive Consumption model at a fixed tariff of $ Cents 3.05 per unit for
                                a period of 25 years from the COD of the entire Contracted Capacity
SCOD                            30th June’2026

Project Business Model

The company proposes to develop the Solar Power Plant under “captive model” wherein it will enter into a Power Purchase Agreement (PPA) with a private customer (Offtaker) under group captive policy which will hold at least 26% stake in the company. An exhibit of Project Business Model is provided hereunder:

Site Location

The project is coming up at Kotha & Harba Villages, Tehsil – Fatehgarh, District – Jaisalmer, Rajasthan. The site is located ~65 km from the Jaisalmer Airport. The site is located at Latitude 26.40° N and Longitude 70.96° E with an Elevation of 226 meters above Mean Sea Level (MSL).

Exhibit: Project Location

The project is located in Jaisalmer district of Rajasthan which is the western region of the state. The climate in this region is Hot Arid with extremely hot temperatures in from April through July. A detail of geographical advantage of setting up Solar Power Project in Jaisalmer is given below:

Table 22: Geographical Advantage of Setting up Solar Project in Jaisalmer

Site Connectivity

The site is well connected through State Highway 21 which is located at an ~5 km distance from the project location. Details regarding site connectivity is given below:

Table 23: Site Connectivity

Our Comments:

Overall access to the project site is considered to be good.

The project site lies within 15 km of the existing 400 kV Fatehgarh substation, allowing short transmission corridors and reduced line-loss exposure. Primary access is via the Jaisalmer–Ramgarh highway and a network of village roads capable of accommodating module and transformer transport.

Land Details

Solar power plants, while being clean and renewable, are very land intensive. The amount of land needed per kilowatt of installed capacity depends on the technology used and the spacing between solar panels (the pitch), which varies with the location's latitude. Sites must be large enough to accommodate the desired power output without sacrificing energy production due to shading between rows of panels.

The area required per kWp of installed power varies with the technology chosen and the distance between rows of modules (the pitch) required avoiding significant inter-row shading varies with the site latitude. Sites should be chosen with sufficient area to allow the required power to be installed without having to reduce the pitch to levels that cause unacceptable yield loss.

A well designed a well-designed Solar Power Plant requires 2.50 acres to 3.00 acres of land for per MWdc of capacity considering the solar panel array, control rooms, infrastructure, and other facilities.

Basis the site location, technology and other aspects envisaged for the project; the estimated land requirement for the entire project is 2300 acres (including land for Pooling Sub-station).

Table 24: Estimated Land Requirements
Particulars                          Area in Acres
Estimated Project Land required for setting up the project    2300
Land already under possession                     2138
Balance Land required to be acquired                  162
Source: Company Information

Table 24: Estimated Land Requirements

Source: Company Information

LSI Comments:

Surface Land requirement per acre of Solar Project complies with prevailing industry standards.

Land acquisition is in a mix of leasehold basis (both Private and Government) along with outright purchase.
 Almost entire land required for the project is in possession of the Company. As informed 
by the Company, balance land will be acquired by December’2025. 
 As per Rajasthan Renewable Energy Policy, 2023, developer shall be permitted to set-up 
Power Project/ Farm on private agriculture land without the requirement of land 
conversion in accordance with the provisions of Rajasthan Tenancy Act 1955 and 
Rajasthan Land Revenue Act 1956 and the rules made there under. 
 Lender(s) to the project to conduct Land Due Diligence as the same is not part our scope 
of work.

Almost entire land required for the project is in possession of the Company. As informed by the Company, balance land will be acquired by December’2025.

As per Rajasthan Renewable Energy Policy, 2023, developer shall be permitted to set-up Power Project/ Farm on private agriculture land without the requirement of land conversion in accordance with the provisions of Rajasthan Tenancy Act 1955 and Rajasthan Land Revenue Act 1956 and the rules made there under.

Lender(s) to the project to conduct Land Due Diligence as the same is not part our scope of work.

Site Selection and Resource Assessment

Site and Location of Solar

The Solar PV plant is a ground mount solar plant having capacity of 840 MWdc/ 600 MWac located at Kotha & Harba Villages, Tehsil – Fatehgarh, District: Jaisalmer in the Indian state of Rajasthan. The PV plant lies around the location of 26.40° N and 70.96° E at an altitude of approximately 226 m above mean sea level.

Solar Resource Assessment

LSI has done the detailed resource assessment study based on the documents shared by the company for the review.

The accuracy of solar energy yield predictions largely relies on the precision of the solar resource dataset utilized. Since solar irradiation data is not currently measured at the proposed power plant site, alternative data sources must be employed to estimate the site’s irradiation levels.

The solar resource at a location can be characterized by parameters such as global horizontal irradiation (GHI), direct normal irradiation (DNI), and Diffuse Horizontal Irradiation (DHI). These parameters are defined as follows:

Global Horizontal Irradiation (GHI):  The global horizontal irradiation is the total solar energy received on a unit area of horizontal surface. It includes energy received from the sun in a direct beam and energy that is received from radiation scattered off the atmosphere arriving from all directions of the sky (diffuse irradiation). The units of GHI are given in kWh/m2. Values are often provided for a period of a day, a month or a year.

Diffused Horizontal Irradiation (DHI): The diffused horizontal irradiation is the energy received from radiation scattered off the atmosphere arriving from all directions of the sky on a unit area of horizontal surface. It is measured in kWh/m2 and values are strongly dependent on weather conditions and the clearness of the air.

Direct Normal Irradiation (DNI): The direct normal irradiation is the total solar energy received on a unit area of surface directly facing the sun. The units of DNI are kWh/m2. The direct normal irradiation is of particular interest for solar installations that track the sun and to concentrating solar technologies as only radiation coming directly from the sun may be focussed by a lens or mirror.

Direct Normal Irradiation (DNI): The direct normal irradiation is the total solar energy received on a unit area of surface directly facing the sun. The units of DNI are kWh/m2. The direct normal irradiation is of particular interest for solar installations that track the sun and to concentrating solar technologies as only radiation coming directly from the sun may be focussed by a lens or mirror.
Global Horizontal Irradiation (GHI): The global horizontal irradiation is the total solar energy received on a unit area of horizontal surface. It includes energy received from the sun in a direct beam and energy that is received from radiation scattered off the atmosphere arriving from all directions of the sky (diffuse irradiation). The units of GHI are given in kWh/m2. Values are often provided for a period of a day, a month or a year.
Diffused Horizontal Irradiation (DHI): The diffused horizontal irradiation is the energy received from radiation scattered off the atmosphere arriving from all directions of the sky on a unit area of horizontal surface. It is measured in kWh/m2 and values are strongly dependent on weather conditions and the clearness of the air.
Global Tilted Irradiation (GTI): The global tilted irradiation is the total solar energy received on a unit area of a tilted surface. It includes direct and diffused irradiation along with ground reflected irradiation. The units of GTI are kWh/m2. A transposition model is used for translating horizontal irradiation to tilted irradiation within PV modelling software.

For modelling of solar PV plants, GHI and DHI are required for calculating the estimated energy yield. In the northern hemisphere, tilting the modules at an angle towards the south increases the total annual global irradiation that is received on the module plane compared to the horizontal plane. This is quantified by the global tilted irradiation. The optimal tilt angle varies primarily with latitude and depends on local weather patterns, ground conditions and plant layout configurations.

Tilted modules also benefit from irradiation reflected from the ground which is dependent on the ground reflectance, or albedo. Albedo and global tilted irradiation are described below. We have independently optimized the tilt angle and the pitch distance through an iterative process of simulations.

Albedo: The ground albedo or reflectance affects the irradiation on a plane when it is tilted from horizontal and increases the GTI. The albedo is highly site and weather dependent, with typical grass coverings giving an albedo of approximately 0.2 and fresh snow giving an albedo of approximately 0.8, meaning that 20% and 80% respectively of the irradiation is reflected back into the atmosphere.

Table 25: Irradiation Data of the Project Site

Source: PVsyst report dated 05-09-2025 as provided by the Company

Our Comments:

The typical range of GHI considered good for setting up a Solar PV Power Plant is 1600 to 2200 kWh/m2. Basis the PVsyst report, the annual sum of GHI is 2055.20 kWh/m2 which is considered adequate for setting up Solar PV Power Plant.

Table 26: Temperature Data of the Project Site

Source: PVsyst report dated 05-09-2025 as provided by the Company

Our Comments:

The typical range of temperature considered good for setting up a Solar PV Power Plant is 25°C to 35°C. Basis the PVsyst report, the yearly average temperature of project site is 27.29°C, which is considered good for setting up Solar PV Power Plant.

Overall Comments on Site Selection and Resource Assessment:

The annual energy yield of a PV plant is significantly influenced by the site's actual solar resource and ambient temperature. For energy estimation purposes, the Solar GIS data source has been utilized.

Design Review of the Project

The plant’s technology philosophy centers on maximizing energy yield while maintaining high system reliability and low maintenance requirements. Each design decision is anchored in bankability, proven field performance, and lifecycle cost optimization.

Solar Modules

The project adopts high-efficiency N-Type TOPcon Dual Glass bifacial modules supplied by Waaree Energies Limited with a nominal power rating of ≈ 690 Wp each, configured for 1,500 V DC operation. Bifacial gain is expected to enhance annual yield by 6–8 % compared to monofacial designs. Modules are mounted on fixed-tilt structures at 20° angle, optimizing capture for latitude ≈ 26° N. The modules conform to IEC 61215 and IEC 61730 standards, with 25-year performance warranties and 0.42 % annual degradation assumption.

Mounting Structures

Hot-dip-galvanized steel mounting structures are adopted with driven piles embedded to 1.8–2.2 m depth depending on soil resistance. The design accounts for wind speeds up to 180 km/h as per IS 875 (Part III). The layout follows a ground-coverage ratio (GCR) of ≈ 0.45–0.5, balancing bifacial gain and land utilization. Each module table comprises four strings of 29 modules, allowing standardized fabrication and rapid installation.

Inverters and Electrical Design

The project uses 188 central inverter units (Model EP-3300-HB-UD) supplied by Sineng Electric Co. Limited, rated ≈ 3.3 MW each, forming the 600 MWac output. Inverters are string-connected to 33 kV transformers through combiner boxes and DC cables sized for ≤ 1.5 % voltage drop. The AC collection system comprises underground XLPE cables feeding into 33 kV switchgear at inverter stations, which aggregate at a 33/400 kV pooling substation. Reactive-power control and harmonic filtering are integrated within the inverter systems to meet grid-code compliance.

SCADA and Monitoring

The plant incorporates a centralized SCADA system for real-time data acquisition, remote control, and predictive maintenance. The system interfaces with inverters, transformers, and meteorological sensors through fiber-optic communication loops. Automated alarms for fault detection and performance deviation enable a data-driven O&M approach. The control room at the PSS serves as the operational nerve center.

Design Optimization

The design philosophy balances module orientation, inter-row spacing, and DC:AC ratio (1.40) to maximize yield while ensuring inverter loading is within bankable limits. Electrical losses across DC and AC networks are assessed at 2.54 % overall. Component placement minimizes cable runs and facilitates parallel construction of array blocks. Engineering drawings and construction method statements follow Indian Grid Code and CEA standards.

Basis the above, the technical specifications of the project is given below:

Table 27: Technical Specifications of the Project

Our Comments:

Waaree Energies Limited (OEM for supply of Solar PV Modules) is one of India’s largest Module Manufacturer having manufacturing capacity of 15.10 GW in India and another 1.60 GW in the United States of America.

Sineng Electric Co. Limited (OEM for supply of Inverters) is a global leader in power electronics, specializing in the development and production of Solar PV Inverters, energy storage inverters and Digital Power Products. Some of the clients served by Sineng are ArcelorMittal Nippon Steel India – 606 MW, Raghanesda Solar Park – 200 MW.

OEMs selected for the project are of repute and well established.

Off-site Transportation Requirements

We were provided plant location details and based on our site we have observed no such issues in local transportation. Primary access is via the Jaisalmer–Ramgarh highway and a network of village roads capable of accommodating module and transformer transport.

Energy Yield Assessment

A review of the Energy Yield Assessment (EYA) based on the report as prepared by TÜV Rheinland (India) Private Limited (TÜV) along with summary of the key aspects for the proposed project is provided as under:

Table 28: Solar Energy Assessment

Energy Simulation Result is given below:

Table 29: Energy Simulation Assessment

Based on the above Energy Simulation Assessment, the projected generation for 25 years is given below:

Table 30: Projected Generation from Solar Plant

Our Comments:

We have been provided with PVsyst report for review and after detailed desktop review our findings are listed below:

Overall performance of the plant seems to be maintained over the next 25 years.

For Solar Energy Assessment, weather data source from SolarGIS has been used.

LSI has done a review of the considered losses and unavailability factors for the generation estimates.

Generation Estimates on P90 (1496.10 GWh) and DC PLF of 20.33% seems to be achievable with smooth operations of the trackers.

Year on year will be 0.42% degradation as per the document provided by company.

Project Infrastructure Integration

The present project is a cohesive integration of generation, evacuation, and operational infrastructure. The engineering approach emphasizes modularity and redundancy so that each subsystem functions independently yet contributes seamlessly to the collective grid output.

Power Evacuation

The project’s 600 MWac output is aggregated at the 33 kV level across distributed inverter stations. Power is then stepped up through multiple 33/400 kV transformers at the pooling substation. A double-bus GIS arrangement ensures reliability and ease of maintenance. Transmission to the interstate grid is executed through a 400 kV overhead line with twin-moose conductors designed for 50 °C ambient operation. The design minimizes transmission losses (< 0.5 %) and incorporates high-speed line-protection relays with remote tripping capability to meet grid-code requirements.

Transmission Line

The project involves construction of 400kV having 36 towers with a Stringing Length of 12.50 kms.

As per project progress as on 31st October’2025, out of the total 36 towers, Foundation of 34 towers has been completed, also ROW for 34 out of 36 towers is also in possession. Further, Erection of 18 towers is completed.

Stringing of 0.05 km out of 12.50 km is completed.

Internal Infrastructure

The internal network comprises gravel-topped roads, storm-water channels, and cable trenches running in parallel corridors. Each array block houses its own inverter-control kiosk and ring-main-unit enclosure. Low-voltage auxiliary supply is distributed from centralized panels located near each inverter group. Foundations for electrical equipment are standardized concrete pedestals suitable for the site’s soil-bearing capacity. Every equipment pad is earthed with 50 mm² copper strips and connected to the plant-wide earthing grid, ensuring fault-current dissipation and personnel safety.

Water Management & Drainage Systems
Given the desert environment, the project includes an optimized rainwater-runoff design using natural slope gradients. Collection trenches direct occasional monsoon flows toward lined percolation pits, improving groundwater recharge. Water-storage reservoirs feed semi-automatic cleaning systems through HDPE pipelines, reducing tanker dependency.

Communication and Control Infrastructure
The SCADA backbone uses a hybrid fiber-optic and wireless communication system. Each inverter station is connected to the central control room via redundant loops to prevent single-point failure. The command center also interfaces with the transmission-utility control hub, allowing remote monitoring of power quality, reactive-power exchange, and frequency variation.

Overall Comments on Project Infrastructure Integration:
Collectively, the infrastructure demonstrates a well-balanced fusion of technical precision and operational flexibility—key indicators of long-term feasibility for utility-scale plants.

Given the desert environment, the project includes an optimized rainwater-runoff design using natural slope gradients. Collection trenches direct occasional monsoon flows toward lined percolation pits, improving groundwater recharge. Water-storage reservoirs feed semi-automatic cleaning systems through HDPE pipelines, reducing tanker dependency.

Communication and Control Infrastructure

The SCADA backbone uses a hybrid fiber-optic and wireless communication system. Each inverter station is connected to the central control room via redundant loops to prevent single-point failure. The command center also interfaces with the transmission-utility control hub, allowing remote monitoring of power quality, reactive-power exchange, and frequency variation.

Overall Comments on Project Infrastructure Integration:

Collectively, the infrastructure demonstrates a well-balanced fusion of technical precision and operational flexibility—key indicators of long-term feasibility for utility-scale plants.

Power Offtake

The company in the present proposal envisages to sell power generated from the solar plant under a Captive/ Group Captive Open Access model by executing a Power Purchase Agreement.

The captive/group open access model for the sale of power generated by solar power plants in India allows companies to generate electricity and use it for their own consumption or supply to a group of users. Here's a summary of the key aspects of this model:

Table 31: Captive/ Group Open Access Model

The company in the present proposal plans to generate solar power and sell it to industrial and commercial consumers through a Captive/Group Captive Open Access Power Purchase Agreement (PPA).

To qualify for this arrangement, the Electricity Act 2003 requires:
1. Equity Ownership: Consumers must hold at least 26% of the company's equity, proportionate to their contracted energy, and have voting rights.
2. Energy Offtake: Consumers must use at least 51% of their contracted energy to be classified as captive users under Indian electricity laws and regulations.

By meeting these conditions, the solar power plant will be considered a Captive Generating Plant.

Equity Ownership: Consumers must hold at least 26% of the company's equity, proportionate to their contracted energy, and have voting rights.

Energy Offtake: Consumers must use at least 51% of their contracted energy to be classified as captive users under Indian electricity laws and regulations.

By meeting these conditions, the solar power plant will be considered a Captive Generating Plant.

Power Delivery Agreement

Power generated from the Solar Plant will be sold to Vedanta Limited (VL) under a Power Delivery Agreement (PDA) executed on 24th March’2023 at a fixed tariff of $ Cents 3.05 per unit for a period of 25 years from the COD of the entire Contracted Capacity.

Vedanta Limited is the flagship company of the Vedanta Group being headed by Mr. Anil Kumar Agarwal. Vedanta Limited has strong financials with Long-Term CRISIL AA/ Watch Developing Credit Rating.

A brief summary of the Power Delivery Agreement so executed is given below:

Table 32: Brief Snapshot of PDA

Our Comments:

Tariff for offtake of Power has been fixed in USD per unit as against standard practice across industry to be in INR per unit. Thus, carrying risk of Exchange Rate Fluctuations. As informed by the Company, it proposes to undertake Hedging Exercise to mitigate the risk.

Scheduled Commissioning Date of the project has been extended till 22nd August’2026 from earlier envisaged date of 30th June’2025.

As per The Electricity Rules’2005, for a power project to qualify as a ‘Captive Generating Plant’, following conditions are to be satisfied:
(i) not less than twenty six percent of the ownership is held by the captive user (s), and
(ii) not less than fifty one percent of the aggregate electricity generated in such plant, determined on an annual basis, is consumed for the captive use:
Further, ‘Ownership’ has been defined to mean as “in relation to a generating station or power plant set up by a company or any other body corporate shall mean the equity share capital with voting rights. In other cases ownership shall mean proprietary interest and control over the generating station or power plant”.

not less than twenty six percent of the ownership is held by the captive user (s), and

not less than fifty one percent of the aggregate electricity generated in such plant, determined on an annual basis, is consumed for the captive use:

Further, ‘Ownership’ has been defined to mean as “in relation to a generating station or power plant set up by a company or any other body corporate shall mean the equity share capital with voting rights. In other cases ownership shall mean proprietary interest and control over the generating station or power plant”.

In the present proposal, the Company is setting up a 600 MWac Solar Power Plant and have for offtake of the same entered into a Power Delivery Agreement with Vedanta Limited for the entire capacity. Thus, fulfilling condition no. (ii) as mentioned above.

At present, Vedanta Limited, i.e., the offtaker has subscribed to Optionally Convertible Redeemable Preference Shares (OCRPS) having an aggregate value of Rs.125.00 crore, which is not Equity Share Capital and also does not qualify for voting rights. Thus, condition no. (i) as mentioned is yet to be satisfied.

“The Company in relation to satisfaction of the conditions mentioned in The Electricity Rules’2005 have replied as under:

The project financing involves an equity contribution from the offtaker (VL), in the form of Optionally Convertible Redeemable Preference Shares (OCRPS) at the initial stage of the project. This approach is being utilized specifically to manage the shareholder structure and ensure the Serentica group maintains its strategic 51% ownership stake in the project company, as the guidelines, offtaker need to be infuse 26% equity into the project and same will be checked at the time of COD and basis that approach the conversion of OCRPS into Pure Equity will be done near to commissioning of the project.

(a) Conversion near to COD: The OCRPS will be converted into common equity upon the Commercial Operation Date (COD). This timing will finalize the required shareholding percentages.

(b) Addressing Project Cost Volatility: Waiting until COD for the final conversion provides a crucial advantage in handling capital variations. Given the potential for both cost savings and cost overruns during the construction phase, fixing the equity structure prematurely would make it difficult for the project company to manage the resulting need to refund or reallocate equity capital.

Basis above, at the time of Commissioning of the project, 26% infusion from offtaker will get complied along with the majority shareholding will be with the Serentica only.”

Thus, in relation to the above, the Company proposes to comply with The Electricity Rules’2005 prior to Commissioning of the Project. Lender(s) to the project to obtain Conversion Certificate from the Company stating that the offtaker has complied with holding minimum 26% Equity Shareholding along with Voting Rights in the Company before Commissioning of the Project.

Balance terms and conditions of the Power Delivery Agreement are in line with Industry Standards.

Vedanta Power Demand Analysis

A summary of Vedanta Power Demand Analysis basis the Market Intelligence & Analytics Report as prepared by CRISIL in July’2023 for Off-taker Evaluation of VAL for a Renewable Energy project is provided below:

Table 33: Vedanta Power Demand Analysis

Source: CRISIL Report, July’2023

Our Comments:

As construed from the above table, VAL as on July’2023 was evaluating procurement of additional ~200 MW of capacity, preferably from renewable sources, to meet growing energy demand and to comply with Renewable Purchase Obligation (RPO) requirements.

Further, the RPO obligation is also to increase from being at 13.25% in 21-22 to 18.00% in 24-25.

Table 34: Landed Cost of Power for VAL

Source: Company Information

Investment Agreement

Details regarding Investment Agreement (IA) executed for the project is given below:

Table 35: Brief Term of IA
Particulars	Details
Nature of
Agreement	Investment agreement
Date	24th March, 2023
Parties	Serentica Renewables India Private Limited (‘SRIPL’),
	Vedanta Limited (‘Captive user’) and
	Serentica Renewables India 9 Private Limited (‘Developer’)
Purpose	SRIPL is engaged in the business of development and operations of
	power plants. Developer is a wholly owned subsidiary of SRIPL.
	Captive User is in the business of production of zinc, lead, and silver.
	Developer and Captive User have executed the Power Delivery
	Agreement dated 24th March 2023 ("PDA") for the Renewable
	Energy project, pursuant to which Developer has agreed to supply
	power to Captive User and Captive User has agreed to consume the
	same.
	For the above purposes, funding the Project and complying with the
	requirements, SRIPL and Captive User shall make the required
	investments in Developer in accordance with this Agreement.
Captive User
Securities	it means the CU OCRPS, CU Alternate Securities, and any other
	Securities held by Captive User
CU OCRPS
(Optionally
convertible
redeemable
preference
shares)	It means the aggregate of CU OCRPS 1, CU OCRPS 1A and CU OCRPS
	2:
	CU OCRPS 1 - means 4,68,00,000 (Four Crore Sixty-Eight Lakh)
	OCRPS that are to be subscribed by Captive User for the CU OCRPS 1
	Subscription Amount of Rs. 46,80,00,000/-
	CU OCRPS 1A - means 4,68,00,000 (Four Crore Sixty-Eight Lakh)
	OCRPS that are to be subscribed by Captive User for the CU OCRPS IA
	Subscription Amount of Rs. 46,80,00,000/-
	CU OCRPS 2 - means 21,84,00,000 (Twenty-One crore Eighty-Four
	Lakh) OCRPS that are to be subscribed by Captive User for the CU
	OCRPS 2 Subscription Amount of Rs. 2,18,40,00,000/-
Subscription to
CU OCRPS 1	Developer hereby agrees to issue and allot to Captive User and
	Captive User agrees to subscribe to CU OCRPS 1 for the CU OCRPS 1
	Subscription Amount on the Closing 1 Date, free and clear of all
	Encumbrances.
Subscription to
CU OCRPS 1A	Developer hereby agrees to issue and allot to Captive User and
	Captive User agrees to subscribe to CU OCRPS 1A for the CU OCRPS
	1A Subscription Amount on the Closing 1A Date, free and clear of all
	Encumbrances.
Subscription to
further
securities (CU
OCRPS 2)	On the terms and subject to the conditions set out in this Agreement
	and subject to achievement of Closing 1 and Closing 1A, Developer
	hereby agrees to issue and allot to Captive User and Captive User
	agrees to subscribe to CU OCRPS 2 for the CU OCRPS 2 Subscription
	Amount on the Closing 2 Date, free and clear of all Encumbrances.
	The issuance of the CU OCRPS 2 to Captive User may be on private
	placement basis or rights issue basis (as the case may be), and as may
	be decided by Developer.
Funding by
SRIPL	The Board shall from time to time procure funding from SRIPL
	through issue of Equity Shares, CCPS, CCDs, OCDs, NCDs or any other
	Securities or a combination thereof by Developer
Additional
terms/
covenants	 The issuance of any CU OCRPS shall be at FMV (fair market
	value)
	 Developer shall be allowed to create different classes of shares
	and issue shares with differential rights (including differential
	voting rights)
	 the Captive User shall waive or forego all Economic Rights on the
	Captive User Securities in accordance with the written
	instructions of the Developer. Captive User shall execute all
	necessary documents/ agreements/ undertakings from time to
	time as may be required by the Developer for the same without
	any demur or protest.
Conversion
event	Conversion of Captive User Securities and/or SRIPL Securities into
	Equity Shares at any time after Closing 2, as may be decided by the
	Board.
Inter se
Holding Ratio	The shareholding ratio in which Captive User and SRIPL hold Equity
	Shares of Developer, as the Board may decide from time to time, such
	that Captive User holds no less than 26% but no more than 49% of
	the Equity Shares and SRIPL (either itself and/ or through SRIPL
	Nominees) holds no more than 74% but no less than 51% of the
	Equity Shares at any given point in time.
Threshold
maintenance	The Captive User shall, at all times, be obligated to hold the Captive
	User Securities in such manner as to ensure compliance with the
	Captive Rules ("Threshold")
Captive user
event of default	Event of default –
	 Event of default as per PDA and failure to rectify such default
	 Failure by Captive User to meet the funding requirements as
	contemplated
	 Failure by Captive User to meet its obligations under this
	Agreement
	 Transfer by Captive User of Captive User Securities, in breach of
	the terms and conditions of this Agreement
	 Transfer by Captive User of this Agreement and/or its rights and
	obligations therein in breach of the terms and conditions of this
	Agreement
	 Any other material breach of the terms of this Agreement
	 Failure to comply with any voting requirement
	 Voiding, termination, frustration, invalidation or cancellation of
	the PDA
Consequences
of captive user
EOD	1. SRIPL shall have the right, but not the obligation to sell all of the
	SRIPL Securities (by issuing a Put Option Exercise Notice to
	Captive User to that effect) to the Captive User and the Captive
	User shall be obligated to purchase such SRIPL Securities at a
	consideration equivalent to 110% of FMV of such SRIPL
	Securities at the time of the issue such Notice.
	2. If in terms of the PDA, Developer decides to terminate the PDA
	by giving a written notice to Captive User on that behalf
	 Captive User shall be liable to pay Developer an amount
	equivalent to the ACCSP for the amount of electricity equal to
	monthly bill for last 12 months from the date of termination
	of the PDA.
	 Additionally, captive user shall identify another captive user
	acceptable to SRIPL to replace Captive User within 12 months
	of such termination of the PDA.
	 The Captive User shall sell all Captive User Securities free
	from all Encumbrances to such Alternate Captive User
	3. In case the Captive User Securities are not transferred to an
	Alternate Captive User within 12 months of termination of PDA,
	then –
	 In the event Captive User has contributed/ infused any funds
	in Developer for subscription of any Captive User Securities
	but against which no Captive User Securities have been issued
	to Captive User, then SRIPL shall be entitled to receive
	amounts equivalent to such contributions as liquidated
	damages from the Captive User.
	 In the event all Captive User Securities stand issued, then –
	-
	Captive User shall pay to SRIPL liquidated damages for
	amounts equivalent to the FMV of Captive User Securities
	as calculated on the date of the Captive User EOD notified
	by SRIPL to the Captive User in writing.
	-
	SRIPL shall have the right, but not the obligation to
	purchase all or part of Captive User Securities free from all
	Encumbrances (by issuing a Call Option Exercise Notice to
	the Captive User to that effect), Captive User shall be
	under an obligation to sell the Captive User Securities to
	such persons for the FMV permissible under Applicable
	Law at relevant point in time.
Developer
Event of default
under the PDA	In case of developer event of default as per PDA, captive user can
	seek transfer of the project in favour of captive user or its nominee
	Captive User shall be entitled to such transfer of the Project through
	purchase of entire SRIPL Securities by Captive User for consideration
	equivalent to 50% FMV of SRIPL Securities existing at the time of
	exercise of its rights to seek transfer of the Project by Captive User.
	The costs and stamp duty for such transfer of SRIPL Securities shall
	be borne by SRIPL.
Put Option
process	In case of transfer of any SRIPL Securities as per agreement is
	envisaged, SRIPL shall have the right but not an obligation to sell to
	Captive User and Captive User shall be obligated to purchase the
	SRIPL Securities ("Put Option Securities") in accordance with the
	agreement by issuing a written notice (the "Put Option Exercise
	Notice") to Captive User to that effect.
Call option
process	In case of transfer of any Captive User Securities is envisaged, SRIPL
	shall have the right but not an obligation, by issuing the " Option
	Exercise Notice" to Captive User requiring it to, and Captive User
	shall be obligated to, sell the Captive User Securities ("Call Option
	Securities”) as per agreement.
Termination	The agreement can be terminated if any of the following event –
	 In the event Closing 1, Closing 1A or Closing 2 is not achieved as
	per agreement
	 In case of termination of PDA
	 On expiry of the term of the PDA
Schedule 1
Shareholding of developer as on the effective date of the agreement:
SN Name of shareholding	No. of
	equity
	shares	%age of
	holding
1	Serentica Renewables India Pvt. Ltd.
		9,999	99.99%
2	Nikita Gupta (nominee of SRIPL)
		1	0.01%
Total
		10,000	100.00%
Schedule 2,3 &
4
Particulars	Terms for CU OCRPS 1, CU OCRPS 1A, CU
	OCRPS 2
Face value (FV)	Rs.10 each
Issue price	To be issued at FMV
Term	Unless redeemed, it shall be 30 years from
	allotment
Dividend	0.0001% of FV of each per annum
Voting rights	No voting rights
Conversion	Optionally Convertible (by board) to equity
	share after closing 2
Conversion ratio	1:1
Redemption	Redeemable in case of:
	- upon expiry unless converted earlier
	- any time at the option by board

6 PROJECT IMPLEMENTATION AND OPERATIONS STRATEGY

Project Implementation Strategy

The company for smooth implementation of the project has engaged the following entities:

Table 36: Project Implementation Entities

Snapshots of the Contract are as under:

Engineering Procurement Construction (EPC) Contract

The Company for implementation of the project have executed an Engineering, Procurement and Construction (EPC) Contract with M/s. Serentica Renewables India Private Limited (SRIPL) on 27th June’2024 as amended on 03rd January’2025 & 03rd November’2025 for setting up a 900 MWdc/ 600 MWac Solar Power Project at an amended cost of Rs.2733.78 crore (including GST). The said EPC was further amended on 03rd November’2025, incorporating project capacity as 840 MWdc/ 600 MWac at an amended cost of Rs.2989.08 crore.

A brief snapshot of the Key Terms of the EPC Contract is given below:

Table 37: Key Terms of EPC Contract for the Project

Source: Original and Amended EPC Contract

Our Comments:

Terms of the EPC Contract are in line with the Industry Standards.

Shared Infra and Evacuation Sharing Agreement

Power Evacuation for the project will be done on Shared Common Infrastructure basis, wherein the Common Evacuation Infrastructure is being developed by Serentica Renewables India Private Limited. The company has executed a Shared Infra and Evacuation Sharing Agreement (SIESA) with Serentica Renewables India Private Limited on 16th August’2024 as amended on 03rd January’2025 at a price of Rs.152.15 crore (excluding GST).

Brief snapshot of the Shared Infra and Evacuation Sharing Agreement is given below:

Table 38: Key Terms of Shared Infra Agreement for the Project

Module Supply Agreement

To secure supply of Solar PV Modules, Serentica Renewables India Private Limited (SRIPL) has executed a Module Supply Agreement (MSA) with Waaree Energies Limited (WAL) on 10th May’2024 for supply of 900 MWdc of Solar PV Modules at a contract price of USD 170.91 Million.

Waaree Energies Limited (WAL) was founded in 1990 and is headquartered in Mumbai. WAL is one of India’s largest Solar Module Manufacturer, with an aggregate installed capacity of 15.10 GW. Manufacturing facilities of WAL are located in Chikli, Surat, Tumb in Nandigram, Gujarat and Noida. Further, WAL also operates a 5.40 GW Cell Manufacturing facility in Gujarat and a 1.60 GW Module Manufacturing facility in the USA.

Some of the major clientele served by WAL include BHEL, AMP Energy, Piramal, Suzlon, Adani, Aditya Birla Group, etc.

CARE Ratings have provided a Long-term rating of CARE A+; Stable to Waaree Energies Limited vide their rating dated 19th March’2025.

A brief snapshot of the Key Terms of the Module Supply Agreement is given below:

Table 39: Key Terms of the Module Supply Agreement (MSA)
Particulars                               Details
Nature of Agreement                       Module Supply Agreement
Parties to the Agreement                  Serentica Renewables India Private Limited (‘SRIPL’ or ‘Buyer’)
                                          Waaree Energies Limited (‘WAL’ or ‘Supplier’)
Date of Agreement                         10th May’2024
Effective Date of Agreement               10th May’2024
Scope of Supply                           The Supplier agrees to sell to the Buyer and the Buyer agrees to
                                          purchase from the Supplier, Modules with the characteristics and
                                          specifications as set out in this Agreement for the corresponding
                                          prices and in the corresponding quantities aggregating to a total
                                          capacity of 900 MWdc on FOR basis, to Site, subject to the terms of
                                          this Agreement and in compliance with the Delivery Schedule.

                                          The Supplier will provide Spare Modules equal to 0.10% of the total
                                          modules ordered, matching the specifications as stated in this
                                          Agreement. These spares will be delivered with the final shipment
                                          and will meet all requirements applicable to regular modules. Their
                                          cost is already included in the Contract Price, and no extra payment is
                                          required from the Buyer.

                                          Note: As against the Contracted Capacity of 900 MWdc, the project is
                                          being set up for 840 MWdc.
Solar Cells                               The Supplier will source or procure solar cells on behalf of the Buyer
                                          as per mutually agreed technical criteria, subject to the Buyer’s
                                          approval of QAP, EL/visual criteria, and vendor list. The Supplier must
                                          earmark and store approved cells in the Buyer’s name, ensure only
                                          these are used for module production, and conduct joint inspection
                                          with the Buyer before dispatch. Any delay due to pending Buyer
                                          approvals will not be attributable to the Supplier. The contract price
                                          already includes variable cell pricing, and any breach of these
                                          conditions will constitute a material breach under the Agreement.
Contract Price                            Basis the above Scope of Supply, total contract price has been fixed
                                          at USD 17,09,10,000 excluding GST (USD 170.91 Million). Breakup
                                          of the Contract Price is given below:

                                          Particulars                                   Qty. (Wp)           USD/ Wp         Total Price (USD)
                                          TOPcon Bifacial G 12 Solar Cell               90,00,00,000        0.0696          6,26,40,000
                                          (Variable Basis) delivered at Waaree Factory
                                          BOS Module (Fixed Basis) including Third      90,00,00,000        0.1203          10,82,70,000
                                          Party Insurance and Freight till site
                                          (Fatehgarh Rajasthan)
                                          Total                                         90,00,00,000        0.1899          17,09,10,000
                                                                                                                          (i.e., USD 170.91 Million)
Payment Terms                             The agreement payment terms basis the above Contract Price is
                                          given below:

                                          Particulars                                   %age of Contract Price
                                          As Advance Amount within 7 days of            28.00%
                                          submission of Corporate Guarantee by the
                                          Supplier equivalent to the said advance
                                          amount
                                          As Advance Amount within 90 days of           7.00%
                                          submission of Corporate Guarantee or as
                                          may be mutually agreed between the parties
                                          Balance Payment including Taxes to be made    65.00%
                                          by the Buyer by issuing irrevocable LC of 30
                                          days, which shall be opened 30 days prior to
                                          commencement of agreed production schedule
                                          (in tranches) or as mutually agreed between
                                          the Parties
                                          Total                                         100.00%
Designated Delivery Point                 Fatehgarh, Jaisalmer, Rajasthan
Manufacturing Facility                    The Supplier shall supply Modules from the manufacturing facility
                                          of Supplier or its affiliates audited and approved in writing by
                                          Buyer. However, in case of an emergency, a written approval shall be
                                          obtained from the Buyer, for providing the Materials either from
                                          other manufacturing facilities of the Supplier.

                                          In the event of a change in the Manufacturing Facility of the
                                          Supplier, the Buyer shall be entitled (but not obligated) to audit and
                                          approve any other facility; and the entire cost in this regard
                                          (including travelling, boarding and lodging) shall be borne by
                                          Supplier. Additionally, in the event of a change in the Manufacturing
                                          Facility, for the purposes of facilitating the auditing of such other
                                          facility by the Buyer for its final approval, the Supplier shall give
                                          minimum advance notice of 3 (three) weeks to the Buyer.
Inspection Rights                         Buyers Right to Inspect:

                                          The Buyer (or its Authorized Representative) shall have the right to
                                          carry out inspections and call for any additional performance and
                                          other applicable tests in accordance with the quality assurance
                                          procedures (“QAP”), in accordance with this agreement.

                                          Supplier Testing and Factory Inspection:

                                          The Supplier must provide the Buyer with a detailed Production
                                          Plan—including manufacturing timelines and testing schedules— at
                                          least 30 days before production begins. The Buyer has the right to
                                          review this plan, request changes, and receive updates whenever the
                                          Supplier makes any modifications. The Supplier must also specify the
                                          exact Production Period, and any changes to these dates must be
                                          communicated within 5 business days.

                                          During production, the Supplier must perform all routine tests as per
                                          the mutually approved Quality Assurance Plan (QAP) and industry
                                          standards. The Buyer, its Authorized Representatives, or a third-party
                                          Inspection Agency (such as STS, CEA, or TUV) may conduct Factory
                                          Inspections at any time during the Production Period, at the Buyer’s
                                          cost. These inspections include incoming component audits, in-
                                          process checks, electrical testing (IV/EL), and final inspections.
                                          The Supplier must make available all relevant documents—bill of
                                          materials, test reports, in-process inspection data, and IEC/type- test
                                          certificates—and must conduct EL and IV testing in the presence of
                                          the Buyer’s team. If any defects or deviations from specifications are
                                          identified, the Supplier is obligated to immediately rectify them in
                                          accordance with the QAP. Importantly, inspection or non-inspection
                                          by the Buyer does not limit the Supplier’s obligations, warranties, or
                                          liability. Only modules manufactured after the Agreement’s Effective
                                          Date will be accepted.
Suppliers Responsibilities                  Following are the Suppliers Responsibilities as per the Agreement:

                                          • the packing of the Modules in a manner suitable for safe delivery
                                          of the Modules at the Desigated Delivery Point and in the case of the
                                          replacement Modules at the Site. The Supplier shall be liable for all
                                          Losses on account of any damage to the Modules arising as the result
                                          of inadequate or improper packing;

                                          • sending a notice to the Buyer setting forth the following information
                                          concerning the Lot: (i) a description of the items contained in such
                                          Lot; (ii) the date of dispatch; (iii) the estimated date of arrival to the
                                          Designated Delivery Point; (iv) the value of the shipment; (v) the
                                          approximate weight and volume (gross and net); (vi) the details of
                                          the transporter; and (ix) the number of the invoices and vehicles at
                                          least 2 (two) Business Days prior to the embarkation of the Modules,
                                          or the Replacement Modules, to the Designated Delivery Point or the
                                          Site (as the case may be).

                                          • taking all necessary actions and paying all transportation and
                                          related logistics costs in connection with the dispatch of the Modules
                                          via standard ground transport from its manufacturing facility to the
                                          Designated Delivery Point, on basis of the incoterms agreed herein
                                          all in compliance with Applicable Law and Prudent Utility Practices;

                                          • procuring at its sole cost and expense, all requisite insurance in
                                          accordance with the terms of this Agreement which provides adequate
                                          coverage in respect of the Modules (including the Replacement
                                          Modules), from its manufacturing facility in Gujarat till Designated
                                          Delivery Point or the Site (as the case may be).

                                          • any demurrage or similar delay charges and fees payable in respect
                                          of the Lot of the Modules (other than the replacement Modules) after
                                          the Free Use Period, due to reasons which are solely attributable to
                                          the Supplier, and any demurrage or similar delay charges and fees
                                          payable in respect of the shipment of any replacement Modules, due
                                          to reasons which are solely and directly attributable to the Supplier;
                                          • ensuring that: (i) the Modules (other than the replacement
                                          Modules) are delivered only to the Designated Delivery Point; and (ii)
                                          the replacement Modules are delivered only to the Site;

                                          • providing all reasonable assistance to the Buyer in the discharge of
                                          its obligations under this Agreement and performing all other
                                          activities required for the Delivery of the Modules in accordance with
                                          the terms of this Agreement at no additional cost to the Buyer;
Buyers Responsibilities                     Following is the Buyers Responsibilities as per the Agreement:

                                          In connection with the Delivery of each Lot of Modules, the Buyer
                                          shall be responsible for paying all applicable Taxes imposed on the
                                          purchase of the Modules (other than on the replacement Modules)
                                          by a Governmental Authority in India and timely issuance of Dispatch
                                          Clearance Certificate pursuant to this Agreement.
Delayed Delivery                          In case the Modules are not delivered within the scheduled Delivery
                                          Date, then for each week (or part thereof) of delay, the Supplier shall
                                          pay liquidated damages @0.50% of the Contract Price per week. The
                                          delay damages shall not exceed more than 5% of the Contract Price.
Transfer of Warranty                      The supplier agrees and consents that the warranties provided shall
                                          be transferred to the Buyer immediately upon delivery of Modules at
                                          Site, subject to that the Supplier has received the full Contract Price.
Force Majeure                             Following are the Force Majeure events as per this agreement:

                                          • War, invasion, armed conflict or act of foreign enemy.
                                          • Revolution, riot, insurrection or other civil commotion, act of
                                          terrorism or sabotage.
                                          • Nuclear explosion, radioactive, chemical radiation.
                                          • Strike or working to rule, etc.
                                          • Lightning, fire, earthquake, unprecedented rains, cloud bursts, etc.
                                          • Explosion.
                                          • Epidemic, pandemic, plague.
                                          • Major accident or breakdown.
                                          • Event or circumstances of a nature analogous to any events set
                                          forth.
Event of Default or Termination           Following are the Suppliers Event of Default:

                                          • Supplier abandons or repudiates the performances of its
                                          obligations herein for a continuous period of more than 30 days.
                                          • Delay in Delivery of the Modules such that the delay damages
                                          payable by the supplier for such damage exceeds the cap of damages.
                                          • Supplier assigns or novates this agreement.
                                          • Failure of the supplier to initiate performance of its obligations
                                          within 30 days in accordance with the timelines set.
                                          • Fails to provide or maintain the Corporate Guarantee.
                                          • Becomes insolvent.
                                          • Is in breach of its representation and warranties.
                                          • Breach of its obligations with respect to compliance with Anti-
                                          Bribery and Corruption Laws.
                                          • Delays in the delivery of modules such that the delay damages
                                          payable by the supplier for such continuing delay exceed the cap as
                                          set out.

                                          Following are the Buyers Event of Default:

                                          • Non-fulfilment of payment obligations for a continuous period of 30
                                          days.
                                          • Buyer becomes insolvent.
                                          • Is in breach of any of its representations and or warranties.
                                          • Assigns or novate or attempts to assigns or novate this agreement.
                                          • Breach on part of the buyer under this agreement which is not
                                          rectified or cured within a 30 days period.
Termination                               If either Party defaults, the non-defaulting Party must issue a Notice
                                          of Default describing the breach, after which both Parties will attempt
                                          to resolve it. If the defaulting Party fails to cure the breach within 30
                                          days of receiving the notice, the non-defaulting Party has the right to
                                          terminate the Agreement.
Assignment                                Neither Party may assign or transfer its rights or obligations under the
                                          Agreement without the other Party’s written consent. However, the
                                          Buyer may freely assign or novate the Agreement—including rights
                                          such as the Module Warranty—to its affiliates, lenders, investors, or a
                                          buyer of the Project, provided pro-rata contract payments are made.
                                          Any assignment made in violation of this clause will be invalid.

Our Comments:

Waaree Energies Limited is a reputed player in the Solar PV Module manufacturing industry having been in the sector for more than 2 decades.

Terms of the Module Supply Agreement are in line with Industry Standards.

Project Implementation Schedule

The project's successful and timely completion can be attributed to:

Acquisition of adequate land for setting up the project.

Arrangement of proper finance for the project.

Finalization of layout for the proposed plant.

Design of utilities and services.

Arrangement of the requisite statutory approvals.

Recruitment of personals.

The project implementation schedule has been drawn to maintain a strict time schedule:

Table 40: Project Implementation Schedule

Our Comments:

The project at present is in its advance stages of Implementation.

Almost entire land required for setting up the project is in possession of the Company, with balance land envisaged to be acquired by December’2025.

Ordering for all the Items have been completed with deliveries and installation work in progress.

Augmentation Infrastructure being developed by Power Grid Corporation of India Limited (PGCIL) will be completed by August’2026, thus, the Company has sufficient to complete and commission the project.

SCOD for the project was originally envisaged as 30th June’2025. REC Limited (existing lender) have vide their Letter No. REC/CO/REN/2025-26/ SRI9PL/92, dated 29-09-2025 have extended the SCOD to 30th June’2026.

Vedanta Limited has provided an extension to the Scheduled Commercial Date of the project till 22nd August’2026.

The final COD may be documented at the time of Financial Closure.

Lender(s) to the project may appoint Lenders Independent Engineer to monitor the progress of the project.
The Company proposes to comply with The Electricity Rules’2005 prior to Commissioning of the Project. Lender(s) to the project to obtain Conversion Certificate from the Company stating that the offtaker has complied with holding minimum 26% Equity Shareholding along with Voting Rights in the Company before Commissioning of the Project.

Status of Approvals

The current status of Statutory Approvals for the present proposal is provided hereunder:

Table 41: Status of Approvals

Our Comments:

Requisite Approvals required at this stage of the project is in possession of the Company.

The present proposal is an Inter State Transmission System (ISTS) Project, wherein, Augmentation Infrastructure is being developed by Power Grid Corporation of India Limited. As per update by Central Transmission Utility of India Limited (CTUIL) vide its letter reference no. CTU/N/5/Conn-INT-1C/2200000020, dated 12-09-2024, the Interim Date of Commissioning of Augmentation Infrastructure is 28-02-2026 and the final date is 22-08-2026. Further, as per Minutes of Meeting of the 34th Joint Co-ordination Committee Meeting for Generation & Transmission Projects of Northern Region issued by CTUIL vide Reference No. CTU/PMG/34th JCC-NR/MoM, dated 01-09-2025, the Augmentation Infrastructure is likely to be commissioned and operational by 22-08-2026. Thus, at present no delay is being anticipated for completion of the same.

Balance Approvals would be obtained at a later stage.

INDUSTRY HIGHLIGHTS

Introduction

Energy is primarily available in two forms vis-à-vis Renewable and Non-renewable sources. Off the forms available to us we still are dependent primarily on non-renewable sources.

Renewable energy derives its sources from Solar, Wind, Tidal Power and Hydro. The energy sources for renewable energy generation are available in abundance and shall be available for generations to come without the threat of there being depleted.

With about 300 clear and sunny days in a year, the calculated solar energy incidence on India's land area is about 5 quadrillion kilowatt-hours (kWh). The solar energy available in a single year exceeds the possible energy output of all of the fossil fuel energy reserves in India.

The demand for power around the world is steadily increasing with enhanced living standards, supported by rapid urbanization. There has been a spurt in the demand for renewable energy since conventional electricity generation methods such as thermal power plants are getting exhausted gradually. In India, solar and wind are the most popular renewable sources of energy. At present, India ranks third in the Renewable Energy Country Attractive Index. The renewable energy market is constantly expanding through efficient collaboration between the government and the private sector.

India has committed to a significant shift in its energy mix, aiming for 50% of its installed power capacity to come from non-fossil fuel sources by 2030. However, in 2023, fossil fuels still dominated India's electricity generation, accounting for 78% of the total. Coal was the primary source, contributing 75% of the generated electricity, making India the second-largest coal-dependent electricity producer in the G20 after South Africa. While clean energy sources like solar, wind, and hydro made up 22% of India's electricity generation mix, this is notably lower than the global average of 39% and the Asian average of 32%.

Renewable Energy & World

The global Renewable Energy market was valued at USD 1056.27 billion in 2023 and is expected to grow at a CAGR of 8.6% during the forecast period (2024-2032).

Global renewable capacity is expected to grow by 2.7 times by 2030, surpassing countries’ current ambitions by nearly 25%, but it still falls short of tripling. Climate and energy security policies in nearly 140 countries have played a crucial role in making renewables cost-competitive with fossil-fired power plants. This is unlocking new demand from the private sector and households, while industrial policies that encourage local manufacturing of solar panels and wind turbines are fostering domestic markets. However, this is not quite sufficient to reach the goal of tripling renewable energy capacity worldwide established by nearly 200 countries at the COP28 climate summit

The embrace of low-carbon fuels and the implementation of rigorous environmental regulations in many developed nations have significantly propelled the renewable energy sector. Over the recent years, the energy generation market has witnessed a rise in the installed capacity of renewable sources, spurred by growing environmental apprehensions and the imperative to alleviate the detrimental effects of Greenhouse Gases (GHG). This has played a crucial role in the growth of the solar and wind energy sectors.

Source: Polaris Market Research

Renewable capacity expansion in the next five years is anticipated to be much faster than what was expected just a year ago. The upward revision is mainly driven by China, the European Union, the United States and India, which are all implementing existing policies and regulatory and market reforms. The renewable capacity additions estimation in the next few years (as per IEA Report’2024) is as follows –

As per International Agency Renewable (IEA) Report of 2024, the share of renewable energy in power generation in the Asia Pacific is expected to increase from 22% in 2023 to 32% in 2030, which is in line with the global trend. As a result, the region retains its position as the third-smallest renewable energy market, surpassing only Eurasia and the Middle East and North Africa.

Renewable Energy in India

Growing population and increased energy demands of India, has made it imperative to look away from traditional power generation sources and increase reliance on renewable energy generation.

India’s energy demand is primarily fulfilled by the Thermal Power Sector, with Coal Fired Power Plants generating nearly 638.88 Billion Units as on 30th September’2025. A share of source wise power generation till 30th September’2025 is provided below:

With a view to focus reduce reliance on thermal power generation and focus on renewable power generation, Ministry of New & Renewable Energy (MNRE) was established. Aim of MNRE is developing and deploying renewable energy to supplement energy requirements. A brief history of MNRE is provided as under:
The Department of Non-conventional Energy Sources (DNES) became the Ministry of Non-conventional Energy Sources in 1982. Subsequently, in 1992, the Ministry of Non-conventional Energy Sources was renamed as the Ministry of New and Renewable Energy. This agency helps in the advancement of renewable energy in order to improve the energy necessities in the country.

As per India Climate & Energy Dashboard functioning under the NITI Aayog, as on September’2025, the total installed capacity of power generation from renewable energy sources such as Solar, Wind, Hydro, and Small Hydro stands at 500889.23 MW.

Solar Energy in India

India is blessed with about 300 clear and sunny days in a year, the calculated solar energy incidence on India's land area is about 5 quadrillion kilowatt-hours (kWh). The solar energy available in a single year exceeds the possible energy output of all of the fossil fuel energy reserves in India. The total potential of India’s Solar Energy Capacity is 7,48,990 MW, against which as on 31-10-2024 the installed capacity is only 98984.39 MW (being at just 13.21%).

During the last decade the trend for installed capacity of Solar Power Plants in India has shown an upward trend. From FY2013-14 to FY2023-24, the net capacity addition has grown at CAGR of 26.47%. A chart depicting the net capacity addition of Solar Power Plants in India from FY14 to FY25 (till 31-10-2024) is provided hereunder:

Source: https://iced.niti.gov.in/energy/electricity/generation/capacity

The National Institute of Energy estimated the country’s solar potential at 748 GW, assuming solar PV modules cover 3% of the geographical surface. India is a perfect location for solar energy because of its location. It has 300 days of sunshine each year, with daily peak electricity use being in the evenings and a seasonal peak in the summer.

Table 42: State Wise Installed Capacity of Solar Power as on 31-10-2024
State/UT Ground Mounted Solar (MW) PM-Surya Ghar Yojna (Solar Rooftop) (MW) Off-grid Solar/KUSUM (MW) Solar Power Total (MW)
Andhra Pradesh 4337.67 224.88 88.34 4650.89
Arunachal Pradesh 0.00 0.00 6.77 1115.00
Assam 126.00 45.33 9.44 180.77
Bihar 146.06 90.00 21.28 257.34
Chhattisgarh 776.60 98.45 390.73 1265.78
Goa 45.50 0.00 1.41 47.86
Gujarat 10223.80 4340.05 89.09 15305.26
Haryana 266.80 722.03 0.00 916.36
Himachal Pradesh 80.68 22.03 34.58 137.29
Jammu & Kashmir 3360.00 0.00 67.00 3623.82
Jharkhand 21.00 93.04 67.00 181.04
Karnataka 8261.33 632.13 36.64 8930.10
Kerala 913.62 24.93 68.96 1261.76
Ladakh 89.00 0.00 0.00 141.29
Madhya Pradesh 3722.99 423.66 102.04 4248.69
Maharashtra 4747.43 2651.81 734.33 8133.57
Manipur 0.95 0.00 1.41 124.24
Meghalaya 0.00 0.21 4.07 395.11
Mizoram 1.96 0.00 6.39 135.82
Nagaland 1.00 0.00 2.17 110.84
Odisha 507.80 58.39 42.19 608.38
Punjab 886.27 408.16 81.36 1375.79
Rajasthan 20473.11 1294.57 805.45 24553.13
Sikkim 2282.00 0.00 137.29 2344.67
Tamil Nadu 8462.92 792.17 68.96 9324.05
Telangana 4360.49 472.90 8.71 4842.10
Tripura 4.78 0.00 11.08 36.94
Uttar Pradesh 2700.02 271.93 315.03 3286.98
Uttarakhand 273.71 19.96 19.96 592.07
West Bengal 230.20 67.13 13.14 310.47
Andaman & Nicobar Islands 35.16 0.27 1.41 35.16
Chandigarh 75.51 0.81 1.46 75.51
Dadra & Nagar Haveli and Daman & Diu 48.12 0.00 0.00 48.12
Delhi 277.09 9.84 1.46 288.39
Lakshadweep 0.00 0.00 0.00 2.52
Puducherry 0.18 0.00 0.00 52.27
Others 45.01 0.00 45.01 45.01
Total 77784.76 12764.68 3284.16 98984.39

Source: https://mnre.gov.in/en/physical-progress/

Stabilisation of Solar Module Prices

Despite domestic manufacturing capacity, India heavily relies on solar module imports, currently fulfilling 80-85% of its demand. This reliance stems from a limited domestic manufacturing base for critical components like polysilicon ingots and wafers, necessitating costly imports. Furthermore, the installed capacity for solar cells within India is insufficient, forcing module manufacturers to import cells primarily from China, followed by Hong Kong and Malaysia.

The government has implemented measures to bolster the domestic solar industry, including increased import duties. This, coupled with the commissioning of new polysilicon production capacities, has contributed to a decline in module prices in the first half of FY24 compared to the previous year. This price reduction is expected to accelerate solar installation rates.

While global module prices began to fall in 2023 following the easing of supply chain disruptions, they remain sensitive to supply from Chinese Original Equipment Manufacturers (OEMs) who dominate the solar PV manufacturing value chain.
However, global inventory levels and expansion plans by Indian players, driven by the Amended and Liberalized Manufacturing Policy (ALMM) and Basic Custom Duty, are expected to keep prices relatively subdued.

However, global inventory levels and expansion plans by Indian players, driven by the Amended and Liberalized Manufacturing Policy (ALMM) and Basic Custom Duty, are expected to keep prices relatively subdued.

Trend of Solar Power Tariff

Solar tariffs in India have become highly competitive and achieved grid parity. This progress is attributed to advancements in technology, economies of scale, and a substantial reduction in the cost of solar cells and modules. A notable decline in solar tariffs has been observed, from INR 6.2 per kWh in Fiscal Year 2015 to INR 3.1 per kWh in Fiscal Year 2024.

Source: MNRE, CareEdge Research

Note: For FY22,FY23 and FY24, tariffs represent an average of projects bid during the resp. periods.

Exhibit: Trend in Solar Tariff

The bid tariff rates during FY23 were around Rs 2.7 - 3 per unit. Whereas in FY22, the bid tariff rates were around Rs. 2.7 per unit, which is 36% higher than FY21 primarily due to the rising equipment pricing, raw material costs, government duties, and interest rates. Despite this, the bid tariff rates remained lower than that of FY15 levels. The current tariffs in the Indian solar sector (hovering at Rs2.50 -3/kWh) have stabilised at rates about 20-30% below the cost of existing thermal power in India, and up to half the price of new coal-fired power.

Table 43: Recent Bidding Trends
SN 
Project Name 
FY24 
Tariff 
(Rs. /kWh) 
1 
NTPC Pan India Solar Tranche-II, 1,500MW 
Mar-24 
2.60 
2 
SECI Pan India Solar Tranche-XIV, 1,500 MW 
Mar-24 
2.58 
3 
MSAPL Maharashtra Solar, 5000 MW (Agricultural Feeder Scheme) 
Mar-24 
3.09 
4 
MSAPL Maharashtra Solar Tranche-I, 208MW (Agricultural Feeder 
Scheme). 
Mar-24 
3.30 
5 
MSAPL Maharashtra Solar Tranche-I, 196MW (Agricultural Feeder 
Scheme) 
Mar-24 
3.08 
6 
MSAPL Maharashtra Solar, 328MW (Agricultural Feeder Scheme) 
Mar-24 
3.09 
7 
MSAPL Maharashtra Solar, 126MW (Agricultural Feeder Scheme) 
Mar-24 
3.08 
8 
MSAPL Maharashtra Solar Tranche-I, 208 MW (Agricultural Feeder 
Scheme) 
Mar-24 
3.09 
9 
MSAPL Maharashtra Solar, 155MW (Agricultural Feeder Scheme) 
Mar-24 
3.09 
10 
MSAPL Maharashtra Solar Tranche-II, 196MW (Agricultural Feeder 
Scheme) 
Mar-24 
3.10 
11 
MSAPL Maharashtra Solar Tranche-II, 170MW (Agricultural Feeder 
Scheme) 
Mar-24 
3.10 
12 
MSAPL Maharashtra Solar Tranche-II, 234MW (Agricultural Feeder 
Scheme) 
Mar-24 
3.10 
13 
MSAPL Maharashtra Solar Tranche-II, 306MW (Agricultural Feeder 
Scheme) 
Mar-24 
3.10 
14 
MSAPL Maharashtra Solar Tranche-II, 170MW (Agricultural Feeder 
Scheme) 
Mar-24 
3.10 
15 
MSAPL Maharashtra Solar Tranche-II, 225MW (Agricultural Feeder 
Scheme) 
Mar-24 
3.10 
16 
SECI Pan India Solar Tranche-XIII, 1,500 MW 
Mar-24 
2.57 
17 
GUVNL Gujarat Solar Tranche-XXIII, 1,125MW 
Mar-24 
2.65 
18 
SJVN Pan India Solar, 1,500MW 
Feb-24 
2.53 
19 
GUVNL Gujarat Solar Tranche-XXI, 600MW 
Jan-24 
2.55 
20 
NTPC Pan India Solar Tranche-I, 1,500MW 
Jan-24 
2.63 
21 
GUVNL Pan India Solar Tranche-XXII, 500MW 
Dec-23 
2.64 
22 
PFCCL Pan India Solar, 1,250MW 
Dec-23 
2.54 
23 
SECI Pan India Solar Tranche-XIII, 1,000 MW 
Dec-23 
2.53 
24 
TANGEDCO Tamil Nadu Solar, 420MW (KUSUM A) 
Nov-23 
3.28 
25 
NHPC Pan India Solar 3,000 MW 
Nov-23 
2.52 
26 
RVUNL Rajasthan Solar 810 MW 
Oct-23 
2.64 
27 
PEDA Multiple States Solar 18 MW 
Sep-23 
3.27 
28 
APDCL Assam Solar Tranche II 50 MW 
Aug-23 
3.92 
29 
APDCL Assam Solar 200 MW 
Aug-23 
3.90 
30 
APDCL Assam Solar 70 MW 
Aug-23 
3.92 
31 
RUVNL Pan India Solar Storage Hybrid 1,200 MW 
Aug-23 
6.68 
32 
RUMS Madhya Pradesh Floating Solar Tranche II 
300 MW 
Aug-23 
3.84 
33 
PSPCL Punjab Solar 200 MW 
Jul-23 
2.75 
34 
PSPCL Pan India Solar Tranche I 1,000 MW 
Jul-23 
2.53 
35 
SECI Pan India Solar Tranche XI 2,000 MW 
Jul-23 
2.60 
36 
GUVNL Gujarat Solar Tranche XX 800 MW 
Jul-23 
2.70 
37 
JDWN Rajasthan Solar 27 MW 
Jun-23 
3.55 
38 
JDWN Rajasthan Solar 31 MW 
Jun-23 
3.48 
39 
AVVNL Rajasthan Solar 40 MW 
May-23 
3.44 
40 
BMC Madhya Pradesh Solar 21 MW 
May-23 
3.47 
41 
RUVNL Rajasthan Solar 1,000 MW 
May-23 
2.61 
42 
GUVNL Gujarat Solar Tranche XVII 600 MW 
May-23 
2.88 
43 
GUVNL Pan India Solar Tranche XIX 500 MW 
Apr-23 
2.72 
44 
MSEDL Maharashtra Solar Tranche X 500 MW 
Apr-23 
2.87 
45 
RECPDCL Pan India Solar 500 MW 
Apr-23 
2.69 
46 
RECPDCL Pan India Solar Tranche I 1,250 MW 
Apr-23 
2.55

Source: CareEdge Research Report

A comparison of Tariff for other Group Captive Projects is given below:

Table 44: Tariff for other Group Captive Projects
Particulars 
Company A 
Company B 
Company C 
Company D 
Company E 
Company F 
Project 
Location 
Ghatanji, 
Maharashtra 
Latur, 
Maharashtra 
Kalaburagi, 
Rajasthan 
Mahidad, 
Gujarat 
Barmer, 
Rajasthan 
Tuticorin, Tamil 
Nadu 
Project 
Capacity 
26.40 MWdc 
75 MWdc 
185.90 MWdc 
70 MWdc 
75 MWdc 
128 MWdc 
Tariff 
Rs.3.45 per unit 
Rs.3.25 per unit 
Rs.3.18 per unit 
Rs.4.00 per unit 
Rs.2.97 per unit 
Rs.2.99 per unit

Source: LSI Internal Data Library

Challenges of Solar Power Plant

Although installation of Solar Power Plant is on the rise and is the need of the hour, there are some challenges too, some of the challenges are detailed as below:

Table 45: Challenges of Solar Power Plant

Government Schemes and Subsidies for Renewables

As part of its Nationally Determined Contribution (NDC) to the Paris Agreement obligations, the government stated that by 2030, reduction of the emissions intensity of GDP by 45% below 2005 levels, and raise the percentage of non-fossil fuels in total capacity to 50% and increase the share of non-fossil power capacity to 50%. Hence the government has pushed towards renewable capacity additions through policy initiatives like JNNSM, obligations of RPO, setting up of SECI, etc.

Under Section 86(1) (e) of the Electricity Act 2003 and the National Tariff Policy 2006, Renewable Purchase Obligation (RPO), is a mechanism by which the obligated entities are obliged to purchase a certain percentage of electricity from renewable energy sources, as a percentage of the total consumption of electricity or buy, in lieu of that, renewable energy certificates (REC) from the market.

RPOs were earlier categorized as solar and non-solar RPOs. However, as per the latest targets, RPOs are categorized as Wind RPO, Hydro RPO, Distributed RPO and Others. Obligated entities (which include distribution companies (or DISCOMs), open access consumers and captive power producers) are obligated to purchase a minimum share of their electricity from renewable energy sources as per RPO targets. The RPO target set for FY18 was 14.25% which was gradually increased to 43.33% for FY30.

Green Energy Corridor

The Green Energy Corridor scheme was launched in 2015 for the setting up of transmission and evacuation infrastructure to facilitate the evacuation of electricity from renewable energy projects. The Intra state transmission system (ISTS) projects have been sanctioned to eight renewable energy states, i.e., Tamil Nadu, Rajasthan, Karnataka, Andhra Pradesh, Maharashtra, Gujarat, Himachal Pradesh, and Madhya Pradesh for evacuation of over 20,000 MW of renewable energy.

As of October, 2023, the project on Green Energy Corridor (GEC) Phase-II – Inter-State Transmission System (ISTS) for 13 GW Renewable Energy Project in Ladakh was approved. The project is targeted to be set up by FY 2029-30 with total estimated cost of Rs.20,773.70 crore and Central Financial Assistance (CFA) @ 40 percent of the project cost i.e. Rs.8,309.48 crore.

This project is in addition to Intra-State Transmission System Green Energy Corridor Phase-II (InSTS GEC- II), which is already under implementation in the States of Gujarat, Himachal Pradesh, Karnataka, Kerala, Rajasthan, Tamil Nadu and Uttar Pradesh for grid integration and power evacuation of approx. 20 GW of RE power and is expected to be completed by 2026. The InSTS GEC-II scheme targets addition of 10753 ckm of transmission lines and 27546 MVA capacity of substations having estimated project cost of Rs.12,031.33 crore and CFA @33%, i.e. Rs.3970.34 crore approved in December 2022.

This project is in addition to Intra-State Transmission System Green Energy Corridor Phase-II (InSTS GEC- II), which is already under implementation in the States of Gujarat, Himachal Pradesh, Karnataka, Kerala, Rajasthan, Tamil Nadu and Uttar Pradesh for grid integration and power evacuation of approx. 20 GW of RE power and is expected to be completed by 2026. The InSTS GEC-II scheme targets addition of 10753 ckm of transmission lines and 27546 MVA capacity of substations having estimated project cost of Rs.12,031.33 crore and CFA @33%, i.e. Rs.3970.34 crore approved in December 2022.

Round-the-Clock-Power (RTC) for RE projects

The round-the-clock power mechanism is a bundling of power that has been bought by the government in order to overcome the issues of intermittency and low capacity utilization of transmission infrastructure. Here, the RE power is bundled with other sources and/or storage. Further, the Government is focusing towards promoting increased adoption of renewable energy and use of green hydrogen as envisaged in the National Green Hydrogen Mission, the Ministry of New and Renewable Energy is working on the modalities for promoting the use of green hydrogen in supporting round-the-clock electricity.

Competitive Bidding Guidelines for Solar and Wind Projects

The bidding guidelines have been issued for long-term procurement of power to promote competitive procurement from solar and wind and also to protect consumer interests. The guidelines for tariff-based competitive bidding process for procurement of power from grid-connected solar PV power projects were issued vide resolution 3rd August 2017 while the guidelines for tariff-based competitive bidding process for procurement of power from grid-connected wind power projects were issued vide resolution dated 8th Dec 2017.

Waiver of ISTS Charges

Ministry of Power has issued an order for an extension to the inter-state transmission system (ISTS) charges waiver on solar and wind energy projects commissioned up to 30 June 2025. Waiver of ISTS charges shall also be allowed for hydro-pumped storage plant and battery energy storage system projects to be commissioned up to 30th June 2025 following some conditions.

ISTS waiver would be allowed for trading electricity generated and supplied from solar, wind, pumped hydro, and Battery Energy Storage Systems (BESS) in the green term ahead market (GTAM) till 30th June 2023 and the arrangement would be reviewed on an annual basis depending on future development in the power market.

As per the notification issued by the Ministry of Power, a complete waiver of ISTS charges has been given for offshore wind power projects commissioned on or before 31st December, 2032 for a period of 25 years from the date of commissioning of the Project.

Must Run Status

In line with the Electricity Act 2003 and the Electricity Grid Code 2010, wind and solar power have the ‘must-run status’. The term ‘must run status’ refers to the notion that electricity evacuation from solar and wind power facilities should not be limited for reasons other than grid safety, equipment or people safety, merit order dispatch, or other commercial concerns.

Government Schemes and Subsidies for Renewables

For Solar Projects

Renewable Energy Growth Drivers

Table 46: Renewable energy growth drivers

Road Ahead

India has set a target to reduce the carbon intensity of the nation’s economy by less than 45% by the end of the decade, achieve 500 GW by 2030, and achieve net-zero carbon emissions by 2070. Low-carbon technologies could create a market worth up to $80 billion in India by 2030.

India’s ambitious renewable energy goals are transforming its power sector. The rising population and widespread electrification in rural homes are fueling the demand for energy to power homes, businesses and communities. Clean energy will reduce pollution levels as villages become self-sustainable with their use of clean energy. In 2022, India's renewable energy sector is expected to boom with a likely investment of US$ 14.5 billion in FY22, as the government focuses on electric vehicles, green hydrogen, and the manufacturing of solar equipment.

It is expected that by 2040, around 49% of the total electricity will be generated by renewable energy as more efficient batteries will be used to store electricity, which will further cut the solar energy cost by 66% as compared to the current cost. The use of renewables in place of coal will save India Rs. 54,000 crore (US$ 8.43 billion) annually. Around 15,000 MW of wind-solar hybrid capacity is expected to be added between 2020-25.

As per the Central Electricity Authority (CEA) estimates, by 2029-30, the share of renewable energy generation would increase from 18% to 44%, while that of thermal is expected to reduce from 78% to 52%. The CEA also estimates India’s power requirement to grow to reach 817 GW by 2030.

REVIEW OF THE COST OF THE PROJECT

Review of the Cost of the Project

Cost estimation provides a vital input to the economic and financial evaluation of the Project. LSI has reviewed the cost estimates as provided by the company. The Project is estimated to be set up at a cost of Rs.3846.51 crore. Components of the same is detailed as under:

Table 47: Components of Project Cost

Cost of Land

Cost of Land for the proposed project is envisaged at Rs.70.00 crore. Land acquisition is in a mix of leasehold basis (both Private and Government) along with outright purchase.

Our Comments:

Initially the cost of land was envisaged at Rs.41.40 crore which has now increased to Rs.70.00 crore. The increase in cost of land is primarily due to the following:

The project involves acquisition of Government Land of ~1142 acres. A District Level Committee Charges (DLC) is levied by the state Government. Over the period of project implementation, the DLC charges have increased by Rs.22000 per acre, thereby increase land cost.

Due to Change in Law, GST @18% on lease rentals being paid to the Lessors is being incurred on Reverse Charge Mechanism basis, thus, increase of land cost.

The project was initially envisaged to be set up using leasehold land, however, due to unavailability, the Company had to procure ~125 acres of land on outright purchase basis.

Increased upfront lease rentals from 2 years to 4 to 5 years.

Out of the envisaged Cost of Land of Rs.70.00 crore, an amount of Rs.510.39 crore (as per Chartered Accountant Certificate dated 06th November’2025, bearing UDIN - 25574308BMJBOU2769, issued by M/s. R. R. Gupta & Co.) has already been incurred towards the project till 30th September’2025.

Cost of EPC

The company has entered into an EPC Contract with Serentica Renewables India Private Limited for execution of the project at a cost of Rs.2989.08 crore (details of EPC Contract is mentioned in Section 5.1.1 of this Report). The cost of EPC has been worked out as under:

Table 48: Components of EPC Cost

Shared Infra and Evacuation Sharing Cost

Cost of Shared Infra and Evacuation Sharing is estimated at Rs.152.15 crore. The company for implementation of the project has executed an Shaed Infra and Evacuation Sharing Agreement with Serentica Renewables India Private Limited (details of Evacuation Sharing Agreement is mentioned in Section 5.1.2 of this Report).

Contingencies

Contingency Provisions estimated for the project is Rs.64.22 crore. Contingency has been calculated @2% of Total Hard Cost of the Project of Rs.3211.23 crore.

Preliminary & Pre-operative Expenses

Preliminary & Pre-operative Expenses envisaged for the project is Rs.109.28 crore. This constitutes the following:

TEV/ LIE/ LLC/ LIA Charges.

Salary During Construction Period.

Insurance During Construction Period.

Approval Costs.

Hedging Costs

Finance Cost

Finance Cost envisaged for the project is Rs.94.04 crore. Finance Cost includes cost towards Loan Processing Fees and Pre-payment Charges to be paid to existing lenders.

Our Comments:

Prepayment Charges: As per existing Sanction of REC Limited dated 16-01-2024, a prepayment charges of 1.00% is applicable in case the prepayment is made within 3 years from the date of 1st Disbursement. As per information provided by the Company, the current outstanding of REC is Rs.1830.31 crore, thus, a prepayment charges of ~Rs.22.00 crore (including GST) is envisaged for the project.

Upfront Fees: As per existing Sanction of REC Limited, a transaction fee of 0.50% of the sanctioned term loan is applicable. Considering term loan amount of Rs.2971.27 crore, upfront fees of ~Rs.18.00 crore (including GST) is envisaged for the project.

Balance Finance Cost of ~Rs.32.00 crore is towards other finance cost.

Interest During Construction (IDC)

IDC for the project is estimated to be at Rs.275.63 crore. Components of IDC is given below:

Table 49: IDC

DSRA

DSRA equivalent to 1 quarter principal repayment and interest (i.e. Rs.80.32 crores) has been considered prior to COD of the project.

Working Capital Margin

Working Capital Margin envisaged for the project is Rs.11.79 crore, calculated @24.68% of total Working Capital Requirement of Rs.44.42 crore.

Project Cost Comparison

A project cost comparison is provided hereunder:

Table 50: Comparison with Other Solar Projects

Source: LSI Internal Data

Our Comments:

The above costs are including GST.

The cost estimated by the Company is comparable with other projects.

MEANS OF FINANCE

The present project entails a capital outlay of Rs.3846.51 crore, which is proposed to be funded in a mix of Promoters Contribution (including Offtakers Contribution) of Rs.769.30 crore and Debt from Bank(s)/ Financial Institution(s) of Rs.3077.21 crore, at a Debt-Equity Ratio of 4:1. Components of Means of Finance is provided as under:

Table 51: Components of Means of Finance

Promoters Contribution (including Offtakers Contribution)

The promoter’s contribution (including contribution) for the project is estimated at Rs.769.30 Crore. As per Chartered Accountant Certificate dated 06th November’2025, an amount of Rs.510.39 crore (being 66.34%) has been incurred towards the project till 30th September’2025. Balance amount of Rs.258.91 crore will be infused in due course of time.  It is proposed to bring in the promoter’s contribution as under:

Table 52: Phasing and Source of Promoters Contribution

Source: Company Information

Our Comments:

Details of total commitment of SRSPL is given below:

Table 53: Total Commitment of SRSPL

Source: Company Information

SRI9PL is part of the Vedanta Group which is a multi-national conglomerate having its presence in various industries. Further, for offtake of power generated from the plant, the company has executed a Power Delivery Agreement with Vedanta Limited (VL) which is a CRISIL AA/ Watch Developing Credit Rated entity.

Considering resourceful and well-established group, the promoters should be able to bring in the funds required for the proposed project.

Note:

As per Chartered Accountant Certificate dated 06th November’2025, bearing UDIN - 25574308BMJBOU2769, issued by M/s. R. R. Gupta & Co., an amount of Rs.510.39 crore has been incurred towards the project till 30th September’2025. Thus, out of the total envisaged Promoters Contribution of Rs.769.30 crore amount already infused towards the project is Rs.510.39 crore (being 66.34%). Balance amount of Rs.258.91 crore will be infused in due course of time.

As construed from the commitment details shared by the Company, around Rs.2883 crore of funds is available with SRSPL for infusion into various projects. Thus, it will be able to bring in the requisite balance funds required for the project.

The lenders may stipulate condition requiring the company to provide necessary undertaking:

That the amount invested into the project till date will not be withdrawn during the pendency of the loan with the bank.

Infusing the balance required contribution (including but not limited to any shortfall of funds by the off-takers/ captive users) from its own sources as well as undertake to bring funds for financing Cost overruns, if any

Debt

The company in the present proposal envisages to raise Term Loan of Rs.3077.21 crore. Debt for the project is proposed to be raised in INR dominated Term Loan of Rs.2461.77 crore and USD dominated Term Loan of Rs.615.44 crore.

Table 54: Indicative INR dominated Terms of Debt
Particulars Details
Amount of Term Loan Rs.2461.77 crore
COD of the Project 30th June’2026
Loan Assumptions
Particulars Details
Drawl Period 9 months
Moratorium from COD 12 months
Repayment Period 228 months (19 years)
Door to Door Tenor 264 months (22 years)
Rate of Interest 8.75% (till COD)
8.25% (post COD)
Repayment Starts Qtr.1 FY28
Repayment Ends Qtr.4 FY46

Table 55: Indicative INR dominated Term Loan Repayment Sheet
Financial Year %age of Repayment Rs. Crore
2028 2.75% 67.70
2029 2.50% 61.54
2030 3.00% 73.85
2031 3.50% 86.16
2032 4.00% 98.47
2033 4.50% 110.78
2034 5.00% 123.09
2035 5.50% 135.40
2036 6.25% 153.86
2037 6.50% 160.02
2038 6.50% 160.02
2039 7.00% 172.32
2040 7.50% 184.63
2041 7.50% 184.63
2042 8.25% 203.10
2043 6.25% 153.86
2044 5.50% 135.40
2045 5.00% 123.09
2046 3.00% 73.85
Total 100.00% 2461.77

Table 56: Indicative USD dominated Terms of Debt
Particulars Details
Amount of Term Loan Rs.615.44 crore
COD of the Project 30th June’2026
Loan Assumptions
Particulars Details
Drawl Period 9 months
Moratorium from COD 12 months
Repayment Period 228 months (19 years)
Door to Door Tenor 249 months (20 years and 9 months)
Rate of Interest 5.00% for the entire tenor of Loan
Repayment Starts Qtr.1 FY28
Repayment Ends Qtr.4 FY46

Table 57: Indicative USD dominated Term Loan Repayment Sheet
Financial Year Rs. Crore
2028 18.39
2029 17.28
2030 21.43
2031 25.84
2032 30.52
2033 35.48
2034 40.74
2035 46.31
2036 54.38
2037 58.44
2038 60.40
2039 67.21
2040 74.42
2041 76.91
2042 87.43
2043 68.44
2044 62.24
2045 58.48
2046 36.26
Total 940.58

*Amount of Repayment of USD Dominated Term Loan is factored in post year-on-year exchange rate fluctuation of 3.30%.

RISK PERCEIVED & SWOT 

Page | 158 
LSI Financial Services Private Limited 
 Serentica Renewables India 9 Private Limited Private & Confidential 
10.1 Risk Perceived & Mitigation 

Table 58: Critical Risk Factors & Mitigation 
Risk Factor 
Level of 
Risk 
Risk Description 
Promoters 
Experience 
Low 
The company is promoted by Serentica Renewables India 
Private Limited (SRIPL) and is part of the Vedanta Group 
which is a multi-national conglomerate having presence in 
various industries. 

SRIPL has an established track record in developing 
renewable power projects. Over the years, the promoters 
have executed projects having capacity of more than 0.50 
GW with another 5 GW under pipeline. 

The present project is setting up Greenfield Renewable 
Solar Power Project having capacity of 840 MWdc/ 600 
MWac located at Jaisalmer, Rajasthan 

Considering the experience of the group in successful 
implementation and operation of existing Renewable 
Energy Generation Projects, risk considered is Low. 
Land 
Identification 
and 
Acquisition 
Low to 
Moderate 
The total estimated land requirement for the project is 
~2300 acres. At present the Company has in its possession 
~2138 acres, balance portion of land has been identified 
and the process of acquisition of the same is under 
progress. As informed by the Company, process of land 
acquisition will be completed by December’2025. 

Considering almost 93% of land is in possession of the 
Company and balance acquisition to be completed by 
December’2025, risk perceived is Low to Moderate. 
Execution of 
Project 
Contracts 
Low 
The Company for successful implementation of the project 
have executed Engineering, Procurement and Construction 
Contract & Shared Infra and Evacuation Sharing 
Agreement with Serentica Renewables India Private 
Limited. 
O&M 
Contract 
will 
be 
executed 
before 
commissioning. 

Since, project implementation contracts have been 
executed, risk perceived is Low. 

Page | 159 
LSI Financial Services Private Limited 
 Serentica Renewables India 9 Private Limited Private & Confidential 
Risk Factor 
Level of 
Risk 
Risk Description 
Equipment & 
Machineries 
Low 
The project is being set up by sourcing equipments from 
reputed OEMs. Solar PV Modules manufactured by Waaree 
Energies Limited are being used along with Inverters of 
Sineng Electric Co. Limited. 

As Equipment and Machineries sourced for the project are 
from OEMs of repute, risk perceived is Low. 
Technology 
Risk 
Low 
The company is setting up the proposed Solar Power Plant 
based on the standard technology accepted across the 
Industry. 

Considering the above, Technology risk is considered Low. 
Power 
Offtake 
Low 
The proposed project entails setting up a Solar Power 
Project having capacity of 600 MWac. The Company for 
offtake of power generated from the project have executed 
a Power Delivery Agreement (PDA) with Vedanta Limited 
for the entire installed capacity at a fixed tariff of $ Cents 
3.05 per unit for a period of 25 years from COD. 

Since, the Company has tie-up to offtake the entire capacity 
of the project, risk perceived is Low. 
Exchange 
Rate 
Moderate 
The project has exposure to foreign currency transactions 
primarily on account of tariff fixed in the PDA at USD per 
unit. Any adverse movement in USD to INR exchange rates 
may reduce the tariff converted to INR and consequently 
impact operating revenue and profitability. Thus, risk 
perceived is Moderate. 

Mitigation: 
To mitigate the above risk, the Company proposes to 
undertake Hedging exercise. 
Group 
Captive 
Status 
Moderate 
to High 
For a power project to qualify as a ‘Captive Generating 
Plant’, it has to satisfy both the following conditions (i) the 
Captive User to hold at least 26% of Equity Share Capital 
with voting rights in the Power Producing Company and 
(ii) at least 51% of the aggregate electricity generated from 
the plant is consumed by the Captive User. 

Page | 160 
LSI Financial Services Private Limited 
 Serentica Renewables India 9 Private Limited Private & Confidential 
Risk Factor 
Level of 
Risk 
Risk Description 
The company for the proposed project has executed a 
Power Delivery Agreement with Vedanta Limited for 
offtake of the entire capacity, thus, fulfilling one of the 
conditions as specified in the Electricity Rules. However, 
the offtaker has till date not subscribed to Equity Share 
Capital in the power producer company i.e., in SRI9PL, 
instead it has invested an amount of Rs.125.00 crore as 
OCRPS. 

As informed by the Company, the above arrangement has 
been undertaken specifically to manage the shareholder 
structure and ensure the Serentica group maintains its 
strategic 51% ownership stake in the project company and 
the conversion of OCRPS into Pure Equity will be done near 
to commissioning of the project. 

Since, the project at present does not qualify to be termed 
as Captive Generating Plant, risk perceived is Moderate to 
High. Lender(s) to the project to obtain Conversion 
Certificate from the Company stating that the offtaker has 
complied with holding minimum 26% Equity Shareholding 
along with Voting Rights in the Company before 
Commissioning of the Project. 
Generation 
Risk 
Low 
The company has carried out PVSyst and Energy Yield 
Assessment Report, the average PLF of the project basis the 
comes to 20.33% at P90 level for DC Capacity. 

The project has an average DSCR of 1.43 in the base case 
thereby having good margin from the lender’s perspective. 

Thus, risk perceived is Low. 
Time 
Overrun 
Low 
The project is in its advanced stage of implementation with 
almost the entire land required in possession of the 
company. Further, execution of project contracts has also 
been completed with deliveries and installation in 
progress. 

Envisaged COD of the project is 30th June’2026, the 
company has sufficient time to complete the project. 

Page | 161 
LSI Financial Services Private Limited 
 Serentica Renewables India 9 Private Limited Private & Confidential 
Risk Factor 
Level of 
Risk 
Risk Description 
Further, it is to be noted that, Vedanta Limited (offtaker) 
has provided approval for extension of COD to 22nd 
August’2026. Thus, risk perceived is Low. 
Cost Overrun 
Low 
The company for implementation of the project has 
executed fixed price EPC and Common Infrastructure 
Sharing Agreements. Thus, risk perceived is Low. 
Statutory 
Approval 
Risk 
Low 
The company at present has in its possession the requisite 
approvals required for the project. Balance approvals such 
as 
First 
Time 
Charging 
Approval, 
Commissioning 
Certificate will be obtained prior to COD. Thus, risk 
perceived is Low. 

Note: 
As per Central Transmission Utility of India Limited, the 
Interim 
Date 
of 
Commissioning 
of 
Augmentation 
Infrastructure is 28-02-2026 and the final date is 22-08-
2026. The company would be required to obtain Temporary 
General Network Access (GNA) Approval, prior to Project 
Commissioning in order to evacuate power before 
completion of Augmentation Infrastructure by Power Grid 
Corporation of India Limited. 
Fund 
Infusion Risk 
Low 
Out of the total envisaged Promoters Contribution of Rs. 
Crore, amount aggregating to Rs.510.39 crore has already 
been infused towards the project till 30th September’2025. 
Balance Promoters Contribution will be infused in due 
course of time. 

Promoters of the company are well established and 
resourceful, thus Fund Infusion Risk is Low. 
Force 
Majeure 
Low 
The company proposes to take out a comprehensive 
insurance policy package during the construction/ 
operations period for the project for insurable Force 
Majeure Events. Thus, risk perceived is Low. 

Page | 162 
LSI Financial Services Private Limited 
 Serentica Renewables India 9 Private Limited Private & Confidential 
10.2 SWOT Analysis 

Table 59: SWOT Analysis 
Strengths 
 SRIPL has an established track record in developing 
renewable power projects with over 0.50 GW of projects 
already commissioned and another 5 GW capacity of 
projects in pipeline 
 Almost entire land required for the project is in 
possession of the Company 
 Project implementation contracts have been executed 
 Power Delivery Agreement for entire capacity of the 
project have been executed 
 Equipments being installed in the project are from well-
established and reputed OEMs 
 Requisite Statutory Approvals required at present stage 
of the project is in possession of the Company 
Weaknesses 
 The project is yet to qualify as ‘Captive Generating Plant’ 
basis the Electricity Rules 
 The project carries Foreign Exchange Fluctuation Risk 
 Solar Energy generation is dependent on Climate 
Conditions which cannot be harnessed during night and 
cloudy as well as stormy days 
Opportunities 
 Govt. of India’s push towards development of renewable 
energy resources 
 Power deficit faced in the country offers opportunity in the 
power sector for renewable energy generation 
 There is favourable demand outlook for the solar power 
sector, driven by competitive tariffs, policy focus and 
initiatives by the commercial and industrial (C&I) 
consumers to reduce dependence on fossil fuels 
Threats 
 Generic threat of Economic Slowdown 
 Govt. policies to remain in force 
 Improvement in productivity and easy adoption of new 
technology may provide competition to solar power 
generation tariff in future 

Page | 163 
LSI Financial Services Private Limited 
 Serentica Renewables India 9 Private Limited Private & Confidential

Risk Perceived & Mitigation

Table 58: Critical Risk Factors & Mitigation
Risk Factor             Level of 
Risk                     Risk Description
Promoters 
Experience              Low                     The company is promoted by Serentica Renewables India
                                                Private Limited (SRIPL) and is part of the Vedanta Group
                                                which is a multi-national conglomerate having presence in
                                                various industries.

                                                SRIPL has an established track record in developing
                                                renewable power projects. Over the years, the promoters
                                                have executed projects having capacity of more than 0.50
                                                GW with another 5 GW under pipeline.

                                                The present project is setting up Greenfield Renewable
                                                Solar Power Project having capacity of 840 MWdc/ 600
                                                MWac located at Jaisalmer, Rajasthan

                                                Considering the experience of the group in successful
                                                implementation and operation of existing Renewable
                                                Energy Generation Projects, risk considered is Low.
Land 
Identification 
and 
Acquisition             Low to 
                        Moderate                The total estimated land requirement for the project is
                                                ~2300 acres. At present the Company has in its possession
                                                ~2138 acres, balance portion of land has been identified
                                                and the process of acquisition of the same is under
                                                progress. As informed by the Company, process of land
                                                acquisition will be completed by December’2025.

                                                Considering almost 93% of land is in possession of the
                                                Company and balance acquisition to be completed by
                                                December’2025, risk perceived is Low to Moderate.
Execution of 
Project 
Contracts               Low                     The Company for successful implementation of the project
                                                have executed Engineering, Procurement and Construction
                                                Contract & Shared Infra and Evacuation Sharing
                                                Agreement with Serentica Renewables India Private
                                                Limited.
                                                O&M
                                                Contract
                                                will
                                                be
                                                executed
                                                before
                                                commissioning.

                                                Since, project implementation contracts have been
                                                executed, risk perceived is Low.
Equipment & 
Machineries             Low                     The project is being set up by sourcing equipments from
                                                reputed OEMs. Solar PV Modules manufactured by Waaree
                                                Energies Limited are being used along with Inverters of
                                                Sineng Electric Co. Limited.

                                                As Equipment and Machineries sourced for the project are
                                                from OEMs of repute, risk perceived is Low.
Technology 
Risk                    Low                     The company is setting up the proposed Solar Power Plant
                                                based on the standard technology accepted across the
                                                Industry.

                                                Considering the above, Technology risk is considered Low.
Power 
Offtake                 Low                     The proposed project entails setting up a Solar Power
                                                Project having capacity of 600 MWac. The Company for
                                                offtake of power generated from the project have executed
                                                a Power Delivery Agreement (PDA) with Vedanta Limited
                                                for the entire installed capacity at a fixed tariff of $ Cents
                                                3.05 per unit for a period of 25 years from COD.

                                                Since, the Company has tie-up to offtake the entire capacity
                                                of the project, risk perceived is Low.
Exchange 
Rate                    Moderate                The project has exposure to foreign currency transactions
                                                primarily on account of tariff fixed in the PDA at USD per
                                                unit. Any adverse movement in USD to INR exchange rates
                                                may reduce the tariff converted to INR and consequently
                                                impact operating revenue and profitability. Thus, risk
                                                perceived is Moderate.

                                                Mitigation:
                                                To mitigate the above risk, the Company proposes to
                                                undertake Hedging exercise.
Group 
Captive 
Status                  Moderate 
                        to High                 For a power project to qualify as a ‘Captive Generating
                                                Plant’, it has to satisfy both the following conditions (i) the
                                                Captive User to hold at least 26% of Equity Share Capital
                                                with voting rights in the Power Producing Company and
                                                (ii) at least 51% of the aggregate electricity generated from
                                                the plant is consumed by the Captive User.

                                                The company for the proposed project has executed a
                                                Power Delivery Agreement with Vedanta Limited for
                                                offtake of the entire capacity, thus, fulfilling one of the
                                                conditions as specified in the Electricity Rules. However,
                                                the offtaker has till date not subscribed to Equity Share
                                                Capital in the power producer company i.e., in SRI9PL,
                                                instead it has invested an amount of Rs.125.00 crore as
                                                OCRPS.

                                                As informed by the Company, the above arrangement has
                                                been undertaken specifically to manage the shareholder
                                                structure and ensure the Serentica group maintains its
                                                strategic 51% ownership stake in the project company and
                                                the conversion of OCRPS into Pure Equity will be done near
                                                to commissioning of the project.

                                                Since, the project at present does not qualify to be termed
                                                as Captive Generating Plant, risk perceived is Moderate to
                                                High. Lender(s) to the project to obtain Conversion
                                                Certificate from the Company stating that the offtaker has
                                                complied with holding minimum 26% Equity Shareholding
                                                along with Voting Rights in the Company before
                                                Commissioning of the Project.
Generation 
Risk                    Low                     The company has carried out PVSyst and Energy Yield
                                                Assessment Report, the average PLF of the project basis the
                                                comes to 20.33% at P90 level for DC Capacity.

                                                The project has an average DSCR of 1.43 in the base case
                                                thereby having good margin from the lender’s perspective.

                                                Thus, risk perceived is Low.
Time 
Overrun                 Low                     The project is in its advanced stage of implementation with
                                                almost the entire land required in possession of the
                                                company. Further, execution of project contracts has also
                                                been completed with deliveries and installation in
                                                progress.

                                                Envisaged COD of the project is 30th June’2026, the
                                                company has sufficient time to complete the project.

                                                Further, it is to be noted that, Vedanta Limited (offtaker)
                                                has provided approval for extension of COD to 22nd
                                                August’2026. Thus, risk perceived is Low.
Cost Overrun            Low                     The company for implementation of the project has
                                                executed fixed price EPC and Common Infrastructure
                                                Sharing Agreements. Thus, risk perceived is Low.
Statutory 
Approval 
Risk                    Low                     The company at present has in its possession the requisite
                                                approvals required for the project. Balance approvals such
                                                as
                                                First
                                                Time
                                                Charging
                                                Approval,
                                                Commissioning
                                                Certificate will be obtained prior to COD. Thus, risk
                                                perceived is Low.

                                                Note:
                                                As per Central Transmission Utility of India Limited, the
                                                Interim
                                                Date
                                                of
                                                Commissioning
                                                of
                                                Augmentation
                                                Infrastructure is 28-02-2026 and the final date is 22-08-
                                                2026. The company would be required to obtain Temporary
                                                General Network Access (GNA) Approval, prior to Project
                                                Commissioning in order to evacuate power before
                                                completion of Augmentation Infrastructure by Power Grid
                                                Corporation of India Limited.
Fund 
Infusion Risk           Low                     Out of the total envisaged Promoters Contribution of Rs.
                                                Crore, amount aggregating to Rs.510.39 crore has already
                                                been infused towards the project till 30th September’2025.
                                                Balance Promoters Contribution will be infused in due
                                                course of time.

                                                Promoters of the company are well established and
                                                resourceful, thus Fund Infusion Risk is Low.
Force 
Majeure                 Low                     The company proposes to take out a comprehensive
                                                insurance policy package during the construction/
                                                operations period for the project for insurable Force
                                                Majeure Events. Thus, risk perceived is Low.

SWOT Analysis

Table 59: SWOT Analysis
Strengths
 SRIPL has an established track record in developing
  renewable power projects with over 0.50 GW of projects
  already commissioned and another 5 GW capacity of
  projects in pipeline
 Almost entire land required for the project is in
  possession of the Company
 Project implementation contracts have been executed
 Power Delivery Agreement for entire capacity of the
  project have been executed
 Equipments being installed in the project are from well-
  established and reputed OEMs
 Requisite Statutory Approvals required at present stage
  of the project is in possession of the Company
Weaknesses
 The project is yet to qualify as ‘Captive Generating Plant’
  basis the Electricity Rules
 The project carries Foreign Exchange Fluctuation Risk
 Solar Energy generation is dependent on Climate
  Conditions which cannot be harnessed during night and
  cloudy as well as stormy days
Opportunities
 Govt. of India’s push towards development of renewable
  energy resources
 Power deficit faced in the country offers opportunity in the
  power sector for renewable energy generation
 There is favourable demand outlook for the solar power
  sector, driven by competitive tariffs, policy focus and
  initiatives by the commercial and industrial (C&I)
  consumers to reduce dependence on fossil fuels
Threats
 Generic threat of Economic Slowdown
 Govt. policies to remain in force
 Improvement in productivity and easy adoption of new
  technology may provide competition to solar power
  generation tariff in future

PROJECT FINANCIALS

Financial Assumptions

COD for the project has been envisaged as 30th June’2026.

Note:

Scheduled Commissioning Date of the project has been extended till 22nd August’2026 from earlier envisaged date of 30th June’2025 by the offtaker (i.e., Vedanta Limited).

PLF of the project

Our Comments:

PLF: PLF for the Project is based on PVsyst Report shared with us.

Annual Degradation: Annual Degradation of 0.42% has been considered based for the project.

Tariff Rates

The company for offtake of power generated from the project have executed a Power Delivery Agreement (PDA) with Vedanta Limited for a period of 25 years at a fixed tariff of $ Cents 3.05 per unit.

Our Comments:

For the purpose of Financial Projections, base rate of Rs.85.00 per USD has been considered. A year-on-year appreciation of 3.30% on exchange rate has been taken. Taking this into consideration USD to INR Conversion rate ranges from Rs.93.70 per USD in FY2027 to Rs.173.63 per USD till FY2046 (end of repayment of Term Loan).

The Company for the purpose of USD Appreciation have considered a year-on-year rate of 3.30%. A calculation of CAGE of USD Exchange rate for the period of year 2005 to 2024 is given below:
Year 	USD to INR
 		CAGR
2005	44.10	3.33%
2006	45.31
2007	41.35
2008	43.51
2009	48.41
2010	45.73
2011	46.67
2012	53.44
2013	56.57
2014	62.33
2015	62.97
2016	66.46
2017	67.79
2018	70.09
2019	70.39
2020	76.38
2021	74.57
2022	81.35
2023	81.94
2024	84.83

As construed from the above table, CAGR for USD Appreciation in the past 20 years has been 3.33%, against which the Company has considered a year-on-year appreciation of 3.30%. Thus, within the range.

O&M Expenses

O&M Expenses for the project is given below:
Particulars 	Unit 	Details 	Escalation %age 	Details
Solar O&M Expenses 	Rs. Crore/ MWdc/ Year 	0.03 	%age 	3%

Our Comments:

O&M Contract for the present proposal will be executed closer to commissioning of the project.

The pricing of O&M is in line with industry standards.

Insurance Expenses
Particulars 	Unit 	Details
Insurance Expenses 	%age of Net Block 	0.15%

Deviation Settlement Mechanism (DSM) Charges

Deviation Settlement Mechanism charges, are fees or penalties applied to electricity generators and consumers who deviate from their scheduled power generation or drawal. For the purpose of Financial Projections, DSM Charges of 0.45% on Revenue has been considered.

ISTS Charges

An ISTS Charges of Rs.0.19 per unit of Electricity Generated. Calculation for the same is given below:
Particulars Units VAL, OD
PPA CUF 28.5%
SPV Name SRIPL 9
ISTS PoC charges for allocation to States ₹ Cr. /month 68.30
LTA Quantum of State MW 2,158
POC Withdrawal Charges payable ₹L/MW/ month 3.16
POC Withdrawal Charges payable ₹L/MW/ year 38
Contracted Capacity MW 600
Monthly PoC charge applicable to customer for delay in operationalisation of connectivity ₹ Cr /month 18.98
Annual RE Generation as per external EYA report MU 1,496
LTOA PoC Charges ₹/unit 1.52
12.50% of Transmission Charges ₹/unit 0.19

Our Comments:

As per Power Delivery Agreement executed with Vedanta Limited (i.e., the offtaker), all the charges post Delivery Point are to be borne by the offtaker. As informed by the Company, it is in the process of applying for waiver of the same. However, on a conservative basis, 12.50% of the total transmission charges has been considered as ISTS Charges in the financial projections.

Rates of Taxes
Particulars Unit Details
Basic Tax Rate %age 22.00%
Add: Surcharge %age 10.00%
Sub-Total %age 24.20%
Add: Cess %age 4.00%
Effective Tax Rate %age 25.17%

Rates of Depreciation
Particulars As per Companies Act As per IT Act
Property, Plant & Equipment 4.32% 40.00%

Holding Levels
Particulars Unit Details
Trade Receivables Months 2.00
Trade Payables Months 1.00

Rate of Interests
Particulars Unit Details
ROI on Term Loan till COD on Rupee Term Loan %age 8.75%
ROI on Term Loan post COD on Rupee Term Loan %age 8.25%
ROI on USD Term Loan for the entire tenor %age 5.00%
Interest on DSRA %age 5.00%

Basis the above assumptions, financial projections for the project are drawn as under.

Projected Profit & Loss Account

Projected Balance Sheet

Projected Cash Flow Statement

Projected DSCR

Levelized Cost of Electricity

Sensitivity Analysis

Our Comments:

As seen from the above table, the company would be able to serve its debt obligations in all the adverse situation. Further, cushion is also available to the lender(s) in the form DSRA built in the project.

CONCLUSION & QR CODE

Conclusion & QR Code

Limitations & Disclaimer

We understand that any prospective operational projection is generally based on expectations of the competitive and economic environments, market dynamics, and other factors that may impact upon the future operations of the project. The assumptions used in the preparation of the projections are based on present circumstances, as to both the most likely set of conditions and the course of action the organisation is most likely to take. In arriving at the financial forecasts, key assumptions have been consistently applied during the estimation period and to the best of our knowledge no factors that may be relevant have been omitted. However, it is usually the case that some events and circumstances do not occur as expected or are not anticipated. Therefore, actual results during the forecast period may differ from that forecasted and such differences may be material. 
We have not verified legal issues pertaining to land, any encumbrances, or statutory issues, if any. We have also not verified legal cases filed by/against the company and its implication on its viability. Banks/Lenders may take note of the same at their end and may stipulate suitable pre/post disbursement conditions to safeguard their interests for recovery of dues and/or timely servicing of loan instalments and interest by the company in future.
Important Findings and our Observations
Based on analysis and assessments in the preceding chapters, the proposed project of Serentica Renewables India 9 Private Limited may be considered to be Technically Feasible and Financially Viable, subject to fulfilment of the underlying basis and assumptions outlined in the previous section(s) of this report.
Considering the projected financial performances which are based on the various assumptions, the company is expected to meet its debt serving obligations towards the project while generating adequate returns well in excess of the cost of borrowing. This is however, subject to the company achieving the projections within the time frame as cited in projections.

Technical Inputs by: Mr Nilanjan Sen

Prepared by: Mr. Rahul Begwani

Date: 24-11-2025

Place: Kolkata

For LSI Financial Services Private Limited

Authorized Signatory

We have not verified legal issues pertaining to land, any encumbrances, or statutory issues, if any. We have also not verified legal cases filed by/against the company and its implication on its viability. Banks/Lenders may take note of the same at their end and may stipulate suitable pre/post disbursement conditions to safeguard their interests for recovery of dues and/or timely servicing of loan instalments and interest by the company in future.

Important Findings and our Observations

Based on analysis and assessments in the preceding chapters, the proposed project of Serentica Renewables India 9 Private Limited may be considered to be Technically Feasible and Financially Viable, subject to fulfilment of the underlying basis and assumptions considered for drawing financial projections and critical project success factors as noted in the previous section(s) of this report.

Considering the projected financial performances which are based on the various assumptions, the company is expected to meet its debt serving obligations towards the project while generating adequate returns well in excess of the cost of borrowing. This is however, subject to the company achieving the projections within the time frame as cited in projections.