The project implementation schedule has been drawn to maintain a strict time schedule:

Table 40: Project Implementation Schedule

Our Comments:

The project at present is in its advance stages of Implementation.

Almost entire land required for setting up the project is in possession of the Company, with balance land envisaged to be acquired by December’2025.

Ordering for all the Items have been completed with deliveries and installation work in progress.

Augmentation Infrastructure being developed by Power Grid Corporation of India Limited (PGCIL) will be completed by August’2026, thus, the Company has sufficient to complete and commission the project.

SCOD for the project was originally envisaged as 30th June’2025. REC Limited (existing lender) have vide their Letter No. REC/CO/REN/2025-26/ SRI9PL/92, dated 29-09-2025 have extended the SCOD to 30th June’2026.

Vedanta Limited has provided an extension to the Scheduled Commercial Date of the project till 22nd August’2026.

The final COD may be documented at the time of Financial Closure.

Lender(s) to the project may appoint Lenders Independent Engineer to monitor the progress of the project.

Status of Approvals

The current status of Statutory Approvals for the present proposal is provided hereunder:

Table 41: Status of Approvals