Project Description

Vedanta Group a multi-national conglomerate operating in various sectors depends heavily on 24x7 power availability to ensure smooth business operations. The group in order to have energy security along with availability of clean and green power and to increase its foothold in the renewable energy sector have incorporated Serentica Renewables India 9 Private Limited for setting up a Solar Power Generating Project having capacity of 840 MWdc/ 600 MWac located at Kotha & Harba Villages, Tehsil – Fatehgarh, District – Jaisalmer, Rajasthan.

Project Snapshot

A brief snapshot of the proposed project is provided as under:

Table 21: Project Snapshot
Particulars                     Details
Project                         Setting up a Solar Power Project having Capacity of 840 MWdc/ 600
                                MWac located at Kotha & Harba Villages, Tehsil – Fatehgarh,
                                District – Jaisalmer, Rajasthan
Location of the Project         Location of the project is described as under:

                                Particulars     Details
                                Villages        Kotha & Harba
                                Tehsil          Fatehgarh
                                District        Jaisalmer
                                State           Rajasthan
                                Latitude        26.40° N
                                Longitude       70.96° E
Land                            The project is being set up on Lease Hold Land admeasuring ~2300
                                acres.

                                At present the company has in its possession 2138 acres of land,
                                balance portion is expected to be acquired by December’2025.
Project Capacity                The present proposal entails setting up the following capacity:

                                Particulars     MWdc    MWac    DC to AC
                                                                Ratio   PLF at P90
                                Project         840     600     1.40    20.33% (at DC level)
                                Capacity                                and 28.46% (at AC
                                                                        level)
Power Evacuation                Power generated from the project shall be evacuated at 400 kV
                                Evacuation voltage level at CTU of Fatehgarh Rajasthan. The total
                                connectivity maximum capacity as approved by CTU is 900 MW.

                                400/33kV plant switchyard shall have two transformer bay, two main
                                bus, one bus coupler and one line bay for the 400kV S/C TL to connect
                                to CTU (approx. 12.50 km)
Transmission Line               The project involves construction of 400kV having 36 towers with a
                                Stringing Length of 12.50 kms.

                                As per project progress as on 31st October’2025, out of the total 36
                                towers, Foundation of 34 towers has been completed, also ROW for 34
                                out of 36 towers is also in possession. Further, Erection of 18 towers is
                                completed.

                                Stringing of 0.05 km out of 12.50 km is completed.
Major Equipment Specifications  The major equipment specification forming part of the Solar Power
                                Plant is provided as under:

                                Particulars     Details
                                Solar PV Modules        690 Wp N-Type TOPcon Bifacial supplied by
                                                        Waaree Energies Limited
                                Inverter                3300 kw Central Inverters supplied by Sineng
                                                        Electric Co. Limited
Power Offtake                   Power generated from the Solar Plant will be sold to Vedanta Limited
                                (VL). A Power Delivery Agreement (PDA) has been executed between
                                SRI9PL and VL for offtake of 600 MWac of Contracted Capacity under
                                Captive Consumption model at a fixed tariff of $ Cents 3.05 per unit for
                                a period of 25 years from the COD of the entire Contracted Capacity
SCOD                            30th June’2026

Project Business Model

The company proposes to develop the Solar Power Plant under “captive model” wherein it will enter into a Power Purchase Agreement (PPA) with a private customer (Offtaker) under group captive policy which will hold at least 26% stake in the company. An exhibit of Project Business Model is provided hereunder: