RISK PERCEIVED & SWOT 

Page | 158 
LSI Financial Services Private Limited 
 Serentica Renewables India 9 Private Limited Private & Confidential 
10.1 Risk Perceived & Mitigation 

Table 58: Critical Risk Factors & Mitigation 
Risk Factor 
Level of 
Risk 
Risk Description 
Promoters 
Experience 
Low 
The company is promoted by Serentica Renewables India 
Private Limited (SRIPL) and is part of the Vedanta Group 
which is a multi-national conglomerate having presence in 
various industries. 

SRIPL has an established track record in developing 
renewable power projects. Over the years, the promoters 
have executed projects having capacity of more than 0.50 
GW with another 5 GW under pipeline. 

The present project is setting up Greenfield Renewable 
Solar Power Project having capacity of 840 MWdc/ 600 
MWac located at Jaisalmer, Rajasthan 

Considering the experience of the group in successful 
implementation and operation of existing Renewable 
Energy Generation Projects, risk considered is Low. 
Land 
Identification 
and 
Acquisition 
Low to 
Moderate 
The total estimated land requirement for the project is 
~2300 acres. At present the Company has in its possession 
~2138 acres, balance portion of land has been identified 
and the process of acquisition of the same is under 
progress. As informed by the Company, process of land 
acquisition will be completed by December’2025. 

Considering almost 93% of land is in possession of the 
Company and balance acquisition to be completed by 
December’2025, risk perceived is Low to Moderate. 
Execution of 
Project 
Contracts 
Low 
The Company for successful implementation of the project 
have executed Engineering, Procurement and Construction 
Contract & Shared Infra and Evacuation Sharing 
Agreement with Serentica Renewables India Private 
Limited. 
O&M 
Contract 
will 
be 
executed 
before 
commissioning. 

Since, project implementation contracts have been 
executed, risk perceived is Low. 

Page | 159 
LSI Financial Services Private Limited 
 Serentica Renewables India 9 Private Limited Private & Confidential 
Risk Factor 
Level of 
Risk 
Risk Description 
Equipment & 
Machineries 
Low 
The project is being set up by sourcing equipments from 
reputed OEMs. Solar PV Modules manufactured by Waaree 
Energies Limited are being used along with Inverters of 
Sineng Electric Co. Limited. 

As Equipment and Machineries sourced for the project are 
from OEMs of repute, risk perceived is Low. 
Technology 
Risk 
Low 
The company is setting up the proposed Solar Power Plant 
based on the standard technology accepted across the 
Industry. 

Considering the above, Technology risk is considered Low. 
Power 
Offtake 
Low 
The proposed project entails setting up a Solar Power 
Project having capacity of 600 MWac. The Company for 
offtake of power generated from the project have executed 
a Power Delivery Agreement (PDA) with Vedanta Limited 
for the entire installed capacity at a fixed tariff of $ Cents 
3.05 per unit for a period of 25 years from COD. 

Since, the Company has tie-up to offtake the entire capacity 
of the project, risk perceived is Low. 
Exchange 
Rate 
Moderate 
The project has exposure to foreign currency transactions 
primarily on account of tariff fixed in the PDA at USD per 
unit. Any adverse movement in USD to INR exchange rates 
may reduce the tariff converted to INR and consequently 
impact operating revenue and profitability. Thus, risk 
perceived is Moderate. 

Mitigation: 
To mitigate the above risk, the Company proposes to 
undertake Hedging exercise. 
Group 
Captive 
Status 
Moderate 
to High 
For a power project to qualify as a ‘Captive Generating 
Plant’, it has to satisfy both the following conditions (i) the 
Captive User to hold at least 26% of Equity Share Capital 
with voting rights in the Power Producing Company and 
(ii) at least 51% of the aggregate electricity generated from 
the plant is consumed by the Captive User. 

Page | 160 
LSI Financial Services Private Limited 
 Serentica Renewables India 9 Private Limited Private & Confidential 
Risk Factor 
Level of 
Risk 
Risk Description 
The company for the proposed project has executed a 
Power Delivery Agreement with Vedanta Limited for 
offtake of the entire capacity, thus, fulfilling one of the 
conditions as specified in the Electricity Rules. However, 
the offtaker has till date not subscribed to Equity Share 
Capital in the power producer company i.e., in SRI9PL, 
instead it has invested an amount of Rs.125.00 crore as 
OCRPS. 

As informed by the Company, the above arrangement has 
been undertaken specifically to manage the shareholder 
structure and ensure the Serentica group maintains its 
strategic 51% ownership stake in the project company and 
the conversion of OCRPS into Pure Equity will be done near 
to commissioning of the project. 

Since, the project at present does not qualify to be termed 
as Captive Generating Plant, risk perceived is Moderate to 
High. Lender(s) to the project to obtain Conversion 
Certificate from the Company stating that the offtaker has 
complied with holding minimum 26% Equity Shareholding 
along with Voting Rights in the Company before 
Commissioning of the Project. 
Generation 
Risk 
Low 
The company has carried out PVSyst and Energy Yield 
Assessment Report, the average PLF of the project basis the 
comes to 20.33% at P90 level for DC Capacity. 

The project has an average DSCR of 1.43 in the base case 
thereby having good margin from the lender’s perspective. 

Thus, risk perceived is Low. 
Time 
Overrun 
Low 
The project is in its advanced stage of implementation with 
almost the entire land required in possession of the 
company. Further, execution of project contracts has also 
been completed with deliveries and installation in 
progress. 

Envisaged COD of the project is 30th June’2026, the 
company has sufficient time to complete the project. 

Page | 161 
LSI Financial Services Private Limited 
 Serentica Renewables India 9 Private Limited Private & Confidential 
Risk Factor 
Level of 
Risk 
Risk Description 
Further, it is to be noted that, Vedanta Limited (offtaker) 
has provided approval for extension of COD to 22nd 
August’2026. Thus, risk perceived is Low. 
Cost Overrun 
Low 
The company for implementation of the project has 
executed fixed price EPC and Common Infrastructure 
Sharing Agreements. Thus, risk perceived is Low. 
Statutory 
Approval 
Risk 
Low 
The company at present has in its possession the requisite 
approvals required for the project. Balance approvals such 
as 
First 
Time 
Charging 
Approval, 
Commissioning 
Certificate will be obtained prior to COD. Thus, risk 
perceived is Low. 

Note: 
As per Central Transmission Utility of India Limited, the 
Interim 
Date 
of 
Commissioning 
of 
Augmentation 
Infrastructure is 28-02-2026 and the final date is 22-08-
2026. The company would be required to obtain Temporary 
General Network Access (GNA) Approval, prior to Project 
Commissioning in order to evacuate power before 
completion of Augmentation Infrastructure by Power Grid 
Corporation of India Limited. 
Fund 
Infusion Risk 
Low 
Out of the total envisaged Promoters Contribution of Rs. 
Crore, amount aggregating to Rs.510.39 crore has already 
been infused towards the project till 30th September’2025. 
Balance Promoters Contribution will be infused in due 
course of time. 

Promoters of the company are well established and 
resourceful, thus Fund Infusion Risk is Low. 
Force 
Majeure 
Low 
The company proposes to take out a comprehensive 
insurance policy package during the construction/ 
operations period for the project for insurable Force 
Majeure Events. Thus, risk perceived is Low. 

Page | 162 
LSI Financial Services Private Limited 
 Serentica Renewables India 9 Private Limited Private & Confidential 
10.2 SWOT Analysis 

Table 59: SWOT Analysis 
Strengths 
 SRIPL has an established track record in developing 
renewable power projects with over 0.50 GW of projects 
already commissioned and another 5 GW capacity of 
projects in pipeline 
 Almost entire land required for the project is in 
possession of the Company 
 Project implementation contracts have been executed 
 Power Delivery Agreement for entire capacity of the 
project have been executed 
 Equipments being installed in the project are from well-
established and reputed OEMs 
 Requisite Statutory Approvals required at present stage 
of the project is in possession of the Company 
Weaknesses 
 The project is yet to qualify as ‘Captive Generating Plant’ 
basis the Electricity Rules 
 The project carries Foreign Exchange Fluctuation Risk 
 Solar Energy generation is dependent on Climate 
Conditions which cannot be harnessed during night and 
cloudy as well as stormy days 
Opportunities 
 Govt. of India’s push towards development of renewable 
energy resources 
 Power deficit faced in the country offers opportunity in the 
power sector for renewable energy generation 
 There is favourable demand outlook for the solar power 
sector, driven by competitive tariffs, policy focus and 
initiatives by the commercial and industrial (C&I) 
consumers to reduce dependence on fossil fuels 
Threats 
 Generic threat of Economic Slowdown 
 Govt. policies to remain in force 
 Improvement in productivity and easy adoption of new 
technology may provide competition to solar power 
generation tariff in future 

Page | 163 
LSI Financial Services Private Limited 
 Serentica Renewables India 9 Private Limited Private & Confidential