Risk Perceived & Mitigation

Table 58: Critical Risk Factors & Mitigation
Risk Factor             Level of 
Risk                     Risk Description
Promoters 
Experience              Low                     The company is promoted by Serentica Renewables India
                                                Private Limited (SRIPL) and is part of the Vedanta Group
                                                which is a multi-national conglomerate having presence in
                                                various industries.

                                                SRIPL has an established track record in developing
                                                renewable power projects. Over the years, the promoters
                                                have executed projects having capacity of more than 0.50
                                                GW with another 5 GW under pipeline.

                                                The present project is setting up Greenfield Renewable
                                                Solar Power Project having capacity of 840 MWdc/ 600
                                                MWac located at Jaisalmer, Rajasthan

                                                Considering the experience of the group in successful
                                                implementation and operation of existing Renewable
                                                Energy Generation Projects, risk considered is Low.
Land 
Identification 
and 
Acquisition             Low to 
                        Moderate                The total estimated land requirement for the project is
                                                ~2300 acres. At present the Company has in its possession
                                                ~2138 acres, balance portion of land has been identified
                                                and the process of acquisition of the same is under
                                                progress. As informed by the Company, process of land
                                                acquisition will be completed by December’2025.

                                                Considering almost 93% of land is in possession of the
                                                Company and balance acquisition to be completed by
                                                December’2025, risk perceived is Low to Moderate.
Execution of 
Project 
Contracts               Low                     The Company for successful implementation of the project
                                                have executed Engineering, Procurement and Construction
                                                Contract & Shared Infra and Evacuation Sharing
                                                Agreement with Serentica Renewables India Private
                                                Limited.
                                                O&M
                                                Contract
                                                will
                                                be
                                                executed
                                                before
                                                commissioning.

                                                Since, project implementation contracts have been
                                                executed, risk perceived is Low.
Equipment & 
Machineries             Low                     The project is being set up by sourcing equipments from
                                                reputed OEMs. Solar PV Modules manufactured by Waaree
                                                Energies Limited are being used along with Inverters of
                                                Sineng Electric Co. Limited.

                                                As Equipment and Machineries sourced for the project are
                                                from OEMs of repute, risk perceived is Low.
Technology 
Risk                    Low                     The company is setting up the proposed Solar Power Plant
                                                based on the standard technology accepted across the
                                                Industry.

                                                Considering the above, Technology risk is considered Low.
Power 
Offtake                 Low                     The proposed project entails setting up a Solar Power
                                                Project having capacity of 600 MWac. The Company for
                                                offtake of power generated from the project have executed
                                                a Power Delivery Agreement (PDA) with Vedanta Limited
                                                for the entire installed capacity at a fixed tariff of $ Cents
                                                3.05 per unit for a period of 25 years from COD.

                                                Since, the Company has tie-up to offtake the entire capacity
                                                of the project, risk perceived is Low.
Exchange 
Rate                    Moderate                The project has exposure to foreign currency transactions
                                                primarily on account of tariff fixed in the PDA at USD per
                                                unit. Any adverse movement in USD to INR exchange rates
                                                may reduce the tariff converted to INR and consequently
                                                impact operating revenue and profitability. Thus, risk
                                                perceived is Moderate.

                                                Mitigation:
                                                To mitigate the above risk, the Company proposes to
                                                undertake Hedging exercise.
Group 
Captive 
Status                  Moderate 
                        to High                 For a power project to qualify as a ‘Captive Generating
                                                Plant’, it has to satisfy both the following conditions (i) the
                                                Captive User to hold at least 26% of Equity Share Capital
                                                with voting rights in the Power Producing Company and
                                                (ii) at least 51% of the aggregate electricity generated from
                                                the plant is consumed by the Captive User.

                                                The company for the proposed project has executed a
                                                Power Delivery Agreement with Vedanta Limited for
                                                offtake of the entire capacity, thus, fulfilling one of the
                                                conditions as specified in the Electricity Rules. However,
                                                the offtaker has till date not subscribed to Equity Share
                                                Capital in the power producer company i.e., in SRI9PL,
                                                instead it has invested an amount of Rs.125.00 crore as
                                                OCRPS.

                                                As informed by the Company, the above arrangement has
                                                been undertaken specifically to manage the shareholder
                                                structure and ensure the Serentica group maintains its
                                                strategic 51% ownership stake in the project company and
                                                the conversion of OCRPS into Pure Equity will be done near
                                                to commissioning of the project.

                                                Since, the project at present does not qualify to be termed
                                                as Captive Generating Plant, risk perceived is Moderate to
                                                High. Lender(s) to the project to obtain Conversion
                                                Certificate from the Company stating that the offtaker has
                                                complied with holding minimum 26% Equity Shareholding
                                                along with Voting Rights in the Company before
                                                Commissioning of the Project.
Generation 
Risk                    Low                     The company has carried out PVSyst and Energy Yield
                                                Assessment Report, the average PLF of the project basis the
                                                comes to 20.33% at P90 level for DC Capacity.

                                                The project has an average DSCR of 1.43 in the base case
                                                thereby having good margin from the lender’s perspective.

                                                Thus, risk perceived is Low.
Time 
Overrun                 Low                     The project is in its advanced stage of implementation with
                                                almost the entire land required in possession of the
                                                company. Further, execution of project contracts has also
                                                been completed with deliveries and installation in
                                                progress.

                                                Envisaged COD of the project is 30th June’2026, the
                                                company has sufficient time to complete the project.

                                                Further, it is to be noted that, Vedanta Limited (offtaker)
                                                has provided approval for extension of COD to 22nd
                                                August’2026. Thus, risk perceived is Low.
Cost Overrun            Low                     The company for implementation of the project has
                                                executed fixed price EPC and Common Infrastructure
                                                Sharing Agreements. Thus, risk perceived is Low.
Statutory 
Approval 
Risk                    Low                     The company at present has in its possession the requisite
                                                approvals required for the project. Balance approvals such
                                                as
                                                First
                                                Time
                                                Charging
                                                Approval,
                                                Commissioning
                                                Certificate will be obtained prior to COD. Thus, risk
                                                perceived is Low.

                                                Note:
                                                As per Central Transmission Utility of India Limited, the
                                                Interim
                                                Date
                                                of
                                                Commissioning
                                                of
                                                Augmentation
                                                Infrastructure is 28-02-2026 and the final date is 22-08-
                                                2026. The company would be required to obtain Temporary
                                                General Network Access (GNA) Approval, prior to Project
                                                Commissioning in order to evacuate power before
                                                completion of Augmentation Infrastructure by Power Grid
                                                Corporation of India Limited.
Fund 
Infusion Risk           Low                     Out of the total envisaged Promoters Contribution of Rs.
                                                Crore, amount aggregating to Rs.510.39 crore has already
                                                been infused towards the project till 30th September’2025.
                                                Balance Promoters Contribution will be infused in due
                                                course of time.

                                                Promoters of the company are well established and
                                                resourceful, thus Fund Infusion Risk is Low.
Force 
Majeure                 Low                     The company proposes to take out a comprehensive
                                                insurance policy package during the construction/
                                                operations period for the project for insurable Force
                                                Majeure Events. Thus, risk perceived is Low.

SWOT Analysis

Table 59: SWOT Analysis
Strengths
 SRIPL has an established track record in developing
  renewable power projects with over 0.50 GW of projects
  already commissioned and another 5 GW capacity of
  projects in pipeline
 Almost entire land required for the project is in
  possession of the Company
 Project implementation contracts have been executed
 Power Delivery Agreement for entire capacity of the
  project have been executed
 Equipments being installed in the project are from well-
  established and reputed OEMs
 Requisite Statutory Approvals required at present stage
  of the project is in possession of the Company
Weaknesses
 The project is yet to qualify as ‘Captive Generating Plant’
  basis the Electricity Rules
 The project carries Foreign Exchange Fluctuation Risk
 Solar Energy generation is dependent on Climate
  Conditions which cannot be harnessed during night and
  cloudy as well as stormy days
Opportunities
 Govt. of India’s push towards development of renewable
  energy resources
 Power deficit faced in the country offers opportunity in the
  power sector for renewable energy generation
 There is favourable demand outlook for the solar power
  sector, driven by competitive tariffs, policy focus and
  initiatives by the commercial and industrial (C&I)
  consumers to reduce dependence on fossil fuels
Threats
 Generic threat of Economic Slowdown
 Govt. policies to remain in force
 Improvement in productivity and easy adoption of new
  technology may provide competition to solar power
  generation tariff in future